## Sheet1
| 1-15 Queen Victoria St and 147-148 Friar St, Reading - External Repairs Project | [15 empty] | Version: | 4 |  | 16.06.2023
Programme
Year | 2023 | [40 empty] | 2024 | [6 empty] | 2025
Month | March | March | April | April | April | April | May | May | May | May | May | June | June | June | June | July | July | July | July | July | August | August | August | August | September | September | September | September | October | October | October | October | October | November | November | November | November | December | December | December | December | January | January | January | January | January | February | February | February
Week commencing | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2025-02-05
External Repairs Project Stages:
Schedule of works | bar: 2023 March to 2023 April
Schedule of works amendments | bar: 2023 April to 2023 May
Tender documents | bar: 2023 April to 2023 April
Information for discharge of conditions | bar: 2023 April to 2023 June
Submit information for discharge of conditions | bar: 2023 June
COUNCIL - Review and discharge relevant planning conditions (8 weeks) | bar: 2023 June to 2023 July
Tender process, contractor site visits (6 weeks) | bar: 2023 May to 2023 June
Tender analysis and report (2 weeks) | bar: 2023 July to 2023 July
CLIENT - Client selection of Contractor following issue of MGC tender report. (1 week) | bar: 2023 July
Contracts prepared and signed (2 weeks) | bar: 2023 July to 2023 July
Contractor mobilisation (1 month) | bar: 2023 August to 2023 August
Construction period (5 months) | bar: 2023 September to 2023 December; 2024 January to 2024 February
Practical Completion | bar: 2024 February
Post completion defects liability period ( 12 months) | 2024 February: 12 months
End of Defects Liability Phase (PC + 12 months) | bar: 2025 February