## Sheet1
Worton Grange - Discharge of Condition tracker
Condition Number | Summary | Submitted to LPA | Discharged | Comments
39 | Time limit
40 | Approved Plans
41 | Materials
| Part 1 Section 278 and Spine Road | Submitted 06/01/2017 | YES 10/03/17 | Materials N/A to Part 1
| Part 2 Trade City | Submitted 06/01/2017 | YES 10/03/17
| Part 3 Retail Unit C | Submitted 06/01/2017 | YES 10/03/17
| Part 4 Hotel, Drive throughs and Bank | Submitted 13/03/2017 |  | Unit D omitted.
Part 5 Car Showrooms
42 | Restriction to sale of bulky goods only to the retail units
43 | Restriction on permitted development
44 | Trading hours - retail
45 | Trading hours - car showrooms
46 | Trading hours - Trade City
47 | Commercial access prior to occupation (roundabout and signalised junction)
48 | Roads provision before occupation
49 | Visibility splays before occupation
50 | Access closure with reinstatement
51 | Footway provision before occupation
52 | Construction Management Statement | Discharged | YES 03.02.17
53 | Parking provision before occupation
Part 1 Section 278 and Spine Road
Part 2 Trade City
Part 3 Retail Unit C
Part 4 Hotel, Drive throughs and Bank
Part 5 Car Showrooms
54 | Car Park/Delivery Management Plan
Unit A - Retail
Unit B - Retail
Unit C - Retail
Unit D - Bank
Unit E - Drive-Thru' Restaurant
Unit F - Hotel / Pub / Coffee Shop
Car Showroom 1
Car Showroom 2
Trade City 1 - 12
55 | Bicycle storage
56 | Employment Travel Plan
Unit A - Retail
Unit B - Retail
Unit C - Retail
Unit D - Bank
Unit E - Drive-Thru' Restaurant
Unit F - Hotel / Pub / Coffee Shop
Car Showroom 1
Car Showroom 2
Trade City 1 - 12
57 | Employment Travel Plan Annual Review
Unit A - Retail
Unit B - Retail
Unit C - Retail
Unit D - Bank
Unit E - Drive-Thru' Restaurant
Unit F - Hotel / Pub / Coffee Shop
Car Showroom 1
Car Showroom 2
Trade City 1 - 12
58 | South - East corner ditch enhancement. | Submitted 06/01/2017 | YES 10/03/17
59 | Sustainable Drainage Implementation | Submitted 06/01/2017 | YES 10/03/17
60 | Sustainable Drainage Scheme
61 a) | Implementation of Approved Remediation Scheme & Validation Report
61 b) | Reporting of Unexpected Contamination - trigger for further submissions
62 | Acoustic assessment of M&E plant
Unit A - Retail
Unit B - Retail
Unit C - Retail
Unit D - Bank
Unit E - Drive-Thru' Restaurant
Unit F - Hotel / Pub / Coffee Shop
Car Showroom 1
Car Showroom 2
Trade City 1 - 12
63 | Hard and Soft Landscaping
| Part 1 Section 278 and Spine Road | Submitted 06/01/2017 | YES 10/03/17 | Hard landscaping n/a to Part 1
| Part 2 Trade City | Submitted 06/01/2017 | YES 10/03/17
| Part 3 Retail Unit C | Submitted 06/01/2017 | YES 10/03/17
| Part 4 Hotel, Drive throughs and Bank | Submitted 13/03/2017 |  | Unit D omitted.
Part 5 Car Showrooms
64 | Landscaping Implementation
65 | Landscape Maintenance and after care
66 | Boundary Treatment
| Part 1 Section 278 and Spine Road | Submitted 06/01/2017 | YES 10/03/17 | Boundary treatment n/a to Part 1
| Part 2 Trade City | Submitted 06/01/2017 | YES 10/03/17
| Part 3 Retail Unit C | Submitted 06/01/2017 | YES 10/03/17
| Part 4 Hotel, Drive throughs and Bank | Submitted 13/03/2017 |  | Unit D omitted.
Part 5 Car Showrooms
67 | Tree Protection Measures adjacent ditch | Discharged | YES 16.09.16
68 | External Lighting Scheme / Wildlife
| Part 1 Section 278 and Spine Road | Submitted 01/02/2017 | YES 10/03/17 | Covered by S278 technical approval.
| Part 2 Trade City | Submitted 01/02/2017 | YES 10/03/17
| Part 3 Retail Unit C | Submitted 01/02/2017 | YES 10/03/17
| Part 4 Hotel, Drive throughs and Bank | Submitted 01/02/2017 | YES 10/03/17
| Part 5 Car Showrooms | Submitted 01/02/2017 | YES 10/03/17
69 | Vegetation to be cleared with regard to bird nesting potential
70 | External Lighting details - road side, pedestrian routes, communal | Submitted 01/02/2017 |  | Main road lighting covered by S278 technical approval
71 | BREEAM Pre-Assessment Report
| Trade City 1 - 12 | Submitted 06/01/2017 | YES 10/03/17
72 | BREEAM Post-Construction Review
Trade City 1 - 12
73 | No bonfires
74 | Archaeology - implementation of approved archaeological scheme | Discharged | YES 20.05.16
75 | Hours of working
76 | Piling Foundation
| Part 1 Section 278 and Spine Road | Submitted 06/01/2017 | YES 10/03/17 | Piling n/a to Part 1
| Part 2 Trade City | Submitted 06/01/2017 | YES 10/03/17 | Piling n/a to Part 2
| Part 3 Retail Unit C | Submitted 06/01/2017 | YES 10/03/17 | Piling n/a to Part 3
| Part 4 Hotel, Drive throughs and Bank | Submitted 06/01/2017 | YES 10/03/17
| Part 5 Car Showrooms | Submitted 06/01/2017 | YES 10/03/17 | Piling n/a to Part 5
77 | Waste Management Plan
Unit A - Retail
Unit B - Retail
Unit C - Retail
Unit D - Bank
Unit E - Drive-Thru' Restaurant
Unit F - Hotel / Pub / Coffee Shop
Car Showroom 1
Car Showroom 2
Trade City 1 - 12
Note on B4: The development hereby approved in full detail (shown on the approved drawings referred to in Condition 40 and hereafter refferred to as "the Detailed Element") must be begun not later than the expiration on three years beginning with the date on which the permission was granted.
Note on B5: The following approved plans relate to the Detailed Element: • 1894-P-20 Site Location Plan • 1894-P-21 Existing Site Plan • 1894-P-22 (B) Proposed Site Plan • Units A & B 1894-P-25 (B) Ground Floor Layout • 1894-P-27 (A) Roof Layout • 1894-P-28 (B) Elevations & Sections • Unit C 1894-P-30 (B) Ground Floor Layout • 1894-P-32 (A) Roof Layout • 1894-P-33 (B) Elevations & Sections • Unit D Bank 1894-P-35 Ground Floor Plan & Roof Layout • 1894-P-36 Elevations • Unit E A3 Unit 1894-P-40 Ground Floor Plan • 1894-P-41 Roof Layout • 1894-P-42 Elevations • Unit F Hotel, Pub & A3 Unit 1894-P-50 Ground & First Floor Plans • 1894-P-51 Second & Third Floor Plans • 1894-P-52 Fourth & Fifth Floor Plans • 1894-P-53 Roof Plan • 1894-P-54 Elevations Sheet 1 of 2 • 1894-P-55 Elevations Sheet 2 of 2 • Trade Counter Units 1894-P-60 TC1-TC6 Ground Floor Plans, Elevations & Section • 1894-P-61 TC7-TC12 Ground Floor Plans, Elevations & • Section 1894-P-62 TC1-TC12 Roof Plans • Car Showroom Plot 1894-P-70 Showroom 1 Ground Floor & Roof Plans • 1894-P-71 Showroom 1 Elevations & Section • 1894-P-72 Showroom 2 Ground Floor & Roof Plans • 1894-P-73 Showroom 2 Elevations & Section • 1894-P-74 Showroom 2 Valet Building • 1894-L-101 Commercial & Residential Footpaths
Note on B6: No commercial unit hereby approved within the Detailed Element shall be developed above ground until details of materials to be used on the external surfaces of that unit have been approved in writing by the local planning authority. The development of each commercial unit shall be carried out in accordance with the relevant approved details.
Note on B12: The retail premise (Units A, B and C) hereby permitted shall not be used for the sale of goods other than: DIY goods and services; garden stock and equipment; furniture (pre-assembled, fitted and self-assembly), fixtures and fittings; floor coverings; household textiles, soft and hard furnishings and homewares; automotive parts and accessories; bicycles, bicycle parts and accessories; electrical goods (including personal mobile communication equipment and accessories); gas appliances; pets, pet goods (including pet food) and pet services; office furniture and equipment; toys and indoor/outdoor play equipment/products; arts and crafts, entertainment and educational goods; sports goods / equipment and sportswear; children and baby goods comprising: puschairs and travel systems; car seats and boosters; feeding equipment; bathing equipment; changing equipment; safety equipment. Goods sold ancillary to the above ranges (such goods to account for no more than 5% of the net sales area of each unit).
Note on B13: Notwithstanding the provisions of Schedule 2, Part 7 Class A of The Town and Country Planning (General Permitted Development) (England) Order 2015 (or any order revoking or re-enacting that Order with or without modification) no extension or enlargement (including alternations to roofs and installation of mezzanine floors) shall be made to the development (retail units A, B and C) hereby permitted.
Note on B14: The retail premises (Units A, B, and C) hereby permitted within the Detailed Element shall not be open for business with the public outside the hours of 0800 and 2200Hrs Mondays to Fridays, 0800 and 2200Hrs Saturdays, 1000 to 1700Hrs Sundays.
Note on B15: The car showroom premises within the Detailed Element shall not be used for the sale of motor vehicles outside the hours of 0800 to 2000Hrs Mondays to Fridays, 0800 to 2000Hrs on Saturdays and 1000 to 1700Hrs on Sundays and Bank Holidays. The premises shall not be used for associated services, repairs and washing preparation outside the hours of 0800 to 1800Hrs Mondays to Fridays, 0800 to 1700Hrs on Saturdays and 1000 to 1600Hrs Sundays and Bank Holidays.
Note on B16: The ‘trade counter’ premises within the Detailed Element hereby permitted may be used flexibly within Classes B1(c), B2 and B8 with provision for up to 10% of the floorspace in each unit to be used for ancillary retail sales. The 'trade counter' premise shall not be open for customers outside the hours of 0700 and 1900Hrs Mondays to Fridays, 0700 to 1800Hrs on Saturdays and 0900 to 1700Hrs on Sundays and Bank Holidays.
Note on B17: No building within the Detailed Element shall be occupied until the roundabout and signalised junction to access the commercial buildings have been constructed in accordance with the approved drawing and in compliance with the requirements of the Local Planning Authority for work carried out within the public highway.
Note on B18: No buildings within the Detailed Element shall be occupied until the access roads associated with the relevant part have been provided in accordance with the approved drawings and in accordance with a timetable to be agreed by the Local Planning Authority.
Note on B19: No building shall be occupied within the Detailed Element until all the visibility splays shown on the approved drawings have been provided. All areas shall thereafter be kept free of all obstructions to visibility over a height of 0.6 metres above the carriageway level.
Note on B20: The existing accesses to the site shall be closed and abandoned prior to first occupation of any commercial land use.
Note on B21: No building within the Detailed Element shall be occupied until a pedestrian footway between 2 metres and 3 metres in width has been constructed for the entire extent as shown annotated in blue on the approved plan ref: 1894-L-101 appended to this decision notice around the comercial site and part of the residential site. Any statutory undertakers’ equipment or street furniture shall be re-sited to provide an unobstructed footway.
Note on B22: No development, with the exception of site clearance, shall take place in any relevant part of the Detailed Element, until a Construction Method Statement for each relevant part within the Detailed Element has been submitted and approved in writing by the local planning authority to provide for: • The parking of vehicles and site operatives and visitors – to be shown on a Plan not less than 1.500; • Loading and unloading of plant and materials used in constructing the development – Areas to be shown on a plan not less than 1.500; • Storage of plant and materials used in constructing the development – Areas to be shown on a plan not less than 1.500; • The erection and maintenance of security hoarding / scaffolding if required. • Wheel washing methods; • Measures on site to control the deposition of dirt / mud on surrounding roads during construction; • Provisions to be made for the control of noise and dust emanating from the site; • Footpath Closures /Road Closures needed during construction; • Traffic Management needed during construction; and • Routes and means of access into and from the site for construction traffic and delivery vehicles (including the removal of waste from the site and methods of preventing deposition of materials on the public highway). The approved Construction Method Statement shall be adhered to throughout the development process subject to any non-substantive changes that may be agreed in writing with the council.
Note on B23: No building within the Detailed Element shall be occupied until vehicle parking spaces have been provided for that building in accordance with a parking schedule/plan to be submitted and approved by the Local Planning Authority. The spaces shall thereafter be kept available for parking at all times.
Note on B29: Prior to occupation of each unit within the Detailed Element details of how and when deliveries, including out of hours deliveries, will be undertaken for that unit without compromising the use of the car park shall be submitted for approval in writing by the local planning authority. Thereafter deliveries will be carried out for that unit in accordance with the approved details.
Note on B39: The covered bicycle storage spaces shown on the approved drawings shall be provided and equipped with secure Sheffield cycle stands before occupation of the unit within the Detailed Element to which they relate.
Note on B40: Within 6 months of first occupation of each unit within the Detailed Element, an employment Travel Plan for each unit shall be submitted to and approved by the local planning authority. The plan shall include a full analysis of the existing modal split for staff, reasons for the modal choice and detailed proposals for future transport provision with the aim of securing reduction in car trips generated to and from the commercial unit.
Note on B50: On the first anniversary of the Employment Travel Plan being approved by the Local Planning Authority it shall be reviewed and thereafter on this anniversary for the life of the development. This, shall include a detailed survey of the number of movements generated by the staff and compared with the initial survey carried out under the terms of the condition above (the control level) and in the event of any reduction not being secured the applicant shall undertake whatsoever measures, as may first have been agreed in writing by the local planning authority, as are necessary to cause a reduction in the number of car borne trips to, as a maximum, the control level. This may include such options as a greater provision of subsidised transport.
Note on B60: Apart from site clearance no development within the Detailed Element shall commence until details of ditch enhancement works for the south west corner have been submitted to and approved in writing by the local planning authority.
Note on B61: Apart from site clearance no development within the Detailed Element shall commence until details of the implementation, maintenance and management plan of the sustainable drainage scheme have been submitted to and approved by the Local Planning Authority. The scheme shall be implemented and thereafter managed and maintained in accordance with the approved plan. The plan shall include: • a timetable for its implementation, and • a management and annual maintenance plan for the lifetime of the development which shall include arrangements to secure the operation of the sustainable drainage scheme throughout its lifetime.
Note on B62: No building hereby permitted within the Detailed Element shall be occupied until the sustainable drainage scheme for the relevant part has been completed in accordance with the submitted and approved details. The sustainable drainage scheme shall be managed and maintained thereafter in accordance with the agreed management and maintenance plan.
Note on B63: a) Implementation of Approved Remediation Scheme The remediation scheme for within the Detailed Element shall be implemented following recommendations made in Waterman Report (Ref: WIB14723-100-R-1-5-1-GH) and in accordance with the approved timetable of works. A validation report (that demonstrates the effectiveness of the remediation carried out) must be submitted to and approved by the Local Planning Authority prior to occupation of the development.
Note on B64: b) Reporting of Unexpected Contamination In the event that contamination not previously identified is found at any time when carrying out the approved development within the Detailed Element, development must be halted on that part of the site and it must be reported in writing to the Local Planning Authority. Following that an assessment of the nature and extent of contamination must be undertaken and where remediation is necessary a remediation scheme, together with a timetable for its implementation, must be submitted to and approved in writing by the Local Planning Authority. The measures in the approved remediation scheme must then be implemented in accordance with the approved timetable. Following completion of measures identified in the approved remediation scheme a validation report must be submitted to and approved in writing by the Local Planning Authority.
Note on B65: Air conditioning or refrigeration plant shall not be installed on any unit within the Detailed Element until an acoustic assessment for the plant for that unit has been submitted to and approved in writing by the local planning authority. The assessment shall demonstrate that the plant noise rating level will not cause an increase in the existing background noise level when measured / predicted in accordance with BS 4142:1997 methodology. The noise levels shall be determined at the nearest noise-sensitive premises. The plant shall be installed and maintained thereafter in accordance with the approved assessment.
Note on B75: Prior to construction of the relevant part within the Detailed Element, details of both hard and soft landscaping shall be submitted to and approved in writing by the Local Planning Authority. Landscape details shall include: • Planting plans • Written specifications (including cultivation and other operations associated with plant and grass establishment) • Schedules of plants and trees, to include large canopy, native and wildlife friendly species, and species likely to prove adaptable to climate change, noting species, planting sizes and proposed numbers / densities, • Full details of tree pits • Details of sustainable drainage and irrigation systems such as rain gardens, and temporary pools and swales • Implementation timetables • Biodiversity enhancements, including integral bird nesting and bat roosting opportunities on and around the new buildings • Specifications for fencing demonstrating how hedgehogs and other wildlife will be able to continue to travel across the site (e.g. fences slightly raised above ground level or with gaps in appropriate locations) • Above and below ground service routes (ensuring they do not conflict with new or existing planting) • Permeable hard surfaces
Note on B81: All hard and soft landscape works within the Detailed Element shall be carried out in accordance with the approved details and to a reasonable standard in accordance with the relevant recommendations of appropriate British Standards or other recognised Codes of Good Practice. The works shall be carried out prior to the occupation of any part of the development or in accordance with the timetable agreed with the Local Planning Authority. Any trees or plants that, within a period of five years after planting, are removed, die or become, in the opinion of the Local Planning Authority, seriously damaged or defective, shall be replaced as soon as is reasonably practicable with others of species, size and number as originally approved or subject to any non-substantive changes that may be agreed in writing with the council.
Note on B82: A landscape management plan within the Detailed Element, including long term design objectives, management responsibilities and maintenance schedules for all landscape areas, shall be submitted to and approved by the Local Planning Authority prior to the occupation of the Detailed Element of the development or any phase of the Detailed Element of the development, whichever is the sooner, for its permitted use.
Note on B83: Prior to commencement of the relevant part of the Detailed Element, details of a plan indicating the positions, design, materials and type of boundary treatment, including details of any security fencing to be erected shall be submitted to, and approved in writing by, the local planning authority. The boundary treatment shall be completed in accordance with a timetable agreed in writing with the local planning authority. Development shall be carried out in accordance with the approved details.
Note on B89: No development shall take place adjacent to the A33 / Basingstoke Road corner within the Detailed Element before the submission and approval of tree protection measures to ensure the off-site trees on the A33/Basingstoke Road corner are protected from any development activity. The approved tree protection measures shall be installed before development on the commercial site begins and retained in place throughout the construction process in accordance with the approved schedule.
Note on B90: Prior to commencement of the relevant part within the Detailed Element, a report detailing the external lighting scheme and how this will not adversely impact upon wildlife shall be submitted to and approved in writing by the local planning authority. The report shall include the following figures and appendices: • A layout plan with beam orientation • A schedule of equipment • Measures to avoid glare • An isolux contour map showing light spillage to 1 lux both vertically and horizontally and areas identified as being of importance for commuting and foraging bats. The approved lighting plan shall thereafter be implemented as agreed.
Note on B96: All areas of hedges, scrub or similar vegetation where birds may nest which are to be removed as part of the Detailed Element of the development, are to be cleared outside the bird-nesting season (March - August inclusive) or if clearance during the bird-nesting season cannot reasonably be avoided, a suitably qualified ecologist will check the areas to be removed immediately prior to clearance and advise whether nesting birds are present. If active nests are recorded, no vegetation clearance or other works that may disturb active nests shall proceed until all young have fledged the nest.
Note on B97: None of the units hereby approved within the Detailed Element shall be occupied until details of external lighting of the site (road side lighting, pedestrian routes and communal areas) have been submitted to and approved in writing by the Local Planning Authority and the lighting implemented in accordance with the approved details. The external lighting shall then be maintained as approved.
Note on B98: No development shall take place on any of the relevant units within the Detailed Element until a BREEAM Pre-Assessment Report for that unit has been submitted to and approved by the Local Planning Authority for that unit to confirm that a BREEAM New Construction Industrial (Shell & Core) 2014 ‘Very Good’ rating of 62.5% will be achieved.
Note on B100: The Detailed Element of the development shall thereafter be carried out to achieve the BREEAM New Construction Industrial (Shell & Core) 2014 rating required by the above condition. Six months post occupation of any commercial unit, as may be approved by the local planning authority, the BREEAM rating achieved will be verified by a post construction review carried out by a licensed assessor.
Note on B102: No materials or green waste produced as a result of the clearance of the Detailed Element of the site, demolition works or construction works associated with the Detailed Element of the development hereby approved shall be burnt on site.
Note on B103: No development shall take place within the Detailed Element site until the applicant, or their agents or their successors in title, has secured and implemented a programme of archaeological work (which may comprise more than one phase of work) in accordance with a written scheme of investigation, which has been submitted to and approved in writing by the Local Planning Authority. The development shall only take place in accordance with the detailed scheme approved pursuant to this condition.
Note on B104: The hours of noisy construction, demolition and associated deliveries within the Detailed Element shall be restricted to the hours of 07:00hrs to 18:00hrs Mondays to Fridays, and 08:00hrs to 13:00hrs on Saturdays, and not at any time on Sundays and Bank or Statutory Holidays without prior approval from the Local Planning Authority.
Note on B105: No development of the relevant part within the Detailed Element shall take place until the method(s) for piling foundations which demonstrate that there would be no resultant unacceptable risk to groundwater quality have been submitted to and approved by the Local Planning Authority. The piling shall thereafter be undertaken only in accordance with the approved details.
Note on B111: Prior to occupation of the units hereby permitted within the Detailed Element a Waste Management Plan in relation to respective units shall be submitted to and approved in writing by the Local Planning Authority. The approved plan shall thereafter be followed for each unit.