| Day 1 | Cover floors, and all working areas. Erect scaffold for contract duration. Begin to secure new lathes Job Specifics, Support entrance Hall ceiling and bathroom Ceiling below false ceiling. |  |
| --- | --- | --- |
| Day 2 | Continue to re-lathe and complete. May go into day 3. |  |
| Day 3 | Continue lathing if required. Apply 1st coat lime render, allow to dry 5-7 days |  |
| Day 4 | Apply 2nd coat lime render, allow to dry 5-7 days |  |
| Day 5 | Apply finish coat, Remove scaffold. Clear down. |  |
| Day 6 | Complete clearing. ( if required) |  |
| Day 7 |  |  |
|  | All timber lathes by Coyle Timber Ltd. All lime materials by Lime Stuff Ltd. |  |

Wheatley Plasterwork Ltd,

Lime Plastering basic works schedule

Job / Ref;   London Road, Reading. Replacement Ceiling.

DESCRIPTION