	Day 1
	Cover floors, and all working areas.
Erect scaffold for contract duration.
Begin to secure new lathes
Job Specifics,
Support entrance Hall ceiling and bathroom 
Ceiling below false ceiling.
	

	Day 2
	Continue to re-lathe and complete.
May go into day 3.
	

	Day 3
	Continue lathing if required.
Apply 1st coat lime render, allow to dry 5-7 days
	

	Day 4
	Apply 2nd  coat lime render, allow to dry 5-7 days
	

	Day 5
	Apply finish coat,
 Remove scaffold.
Clear down.

	

	Day 6
	Complete clearing. ( if required)
	

	Day 7
	
	

	
	 All timber lathes by Coyle Timber Ltd.
[bookmark: _GoBack]All lime materials by Lime Stuff Ltd.              
                                           
	


Wheatley Plasterwork Ltd,
Lime Plastering basic works schedule

Job / Ref;   London Road, Reading. Replacement Ceiling.

                                           DESCRIPTION                    
