Discharge of Conditions  St Peters avenue RG4 7DP 
Application No. 150172
CMS

No.5 

No development shall take place inc demolition works until a construction method statement has been submitted.

A) Parking of vehicles and site operatives and visitors
99 St. Peters Road is on the corner and access will be via the entrance on Woodcote Road. The access point will be secured at all times when not in use and manned when open. Parking will be on St peters avenue in the unrestricted areas highlighted below
Parking  for site operatives will be in the Mapleduram playing fields carpark just up the Woodcote road. , trades man will up load tool etc on site in the loading area and park their vehicles of site ( unless possible to be on site ) [image: C:\Users\User\AppData\Local\Microsoft\Windows\INetCache\IE\B1PVJNNJ\DSC_0194.JPG]



B)  Loading and unloading of materials

All unloading and loading of materials will take place on site and off road. Banks man will be used for traffic in and out of the site. Deliveries will be where possible kept outside of the peak 7.30 -8.30 am  morning rush hour. Shown below. As per below all Care will be taken when working around all remaining trees, flora and fauna.

C) Storage of plant and Materials
As highlight in the drawing below in Orange , as per below  storage of plant and materials  will take place on site . Care will be taken when working around all remaining trees, flora and fauna.

D) 99 St peters avenue already has a 6 foot fence surrounding the property. A Haras fence gate will be used to secure the main entrance 
E) Wheel washing in the Blue area will limit the dirt on to the highway. This will be manned on every delivery and collection. 
F) Measures to control dirt on to public highways, prior to demolition hard standing will be created within the site from Crushed concrete or similar, for vehicles to drive on. Banks man to sweep entrance and exit to public highway during the working day, 
G) Footpath/road closures > Will not be required
H) Traffic management during construction.   Will not be required. A banks man will be present to assist larger vehicles leaving and entering the site. Delivery times/routes.  Deliveries Will not be made to site between 7:30 -9:00am and 4:30-6:00pm, Monday to Friday within peak hours.  Vehicular traffic to inc waste and deliveries will enter the site from woodcote road and park on site , in the areas mentioned on hard standing. 
N.B  the construction of the buildings will be of timber frame construction with off site exterior finishes, so onsite works will mostly be internal. 
Tree and root protection. 
Care will be taken when working around all remaining trees, flora and fauna , tre protection scheme already submitted.   No. Dig area with cellular confinement system will be in place prior to construction to allow ease of movement around the site. ( all demolition will happen clear of the tree protection area and waste removal at the other end of the site. ) See Page 30 of doc PRI19866  attached 
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1. Executive Summary 


1.1. ACD was initially instructed, to carry out a tree survey, and present constraints details 
in accordance with BS5837:2012 Trees in relation to design, demolition and 
construction. This was to identify the quality and value of existing trees on site, 
allowing decisions to be made as to the retention or removal of trees during 
development. Subsequently, the subject layout has been produced and is in line with 
recommendations of the British Standard. Adequate protection can be provided to 
ensure all retained trees are protected throughout development. 


1.2. The single house is to be replaced with two residential dwellings. Trees to be removed 
are limited to low quality trees, which have a limited life and current landscape value.  


1.3. Some site supervision will be required during the removal of the existing hard features 
within the RPA of T1 and the no-dig drive surfacing. 


1.4. The relationship between the building and retained trees is sustainable and is not 
likely to result in any pressure to prune requests from future occupants. 


1.5. The arboricultural method statement and tree protection plan include details of all tree 
protection measures required. 


1.6. The fencing and ground protection must be erected after tree removals and surgery 
but before any demolition or construction contractor enter the site, and before any 
soil stripping takes place.   


1.7. There will be no changes in levels, service routing, machine activity, storage of 
materials or site hut positioning within areas to be protected, and the protective 
fencing shall remain in position for the duration of the construction process.   
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2. Introduction 


2.1. Boyes Developments instructed ACD Arboriculture in April 2015 to prepare the 
following impact assessment. 


2.2. Following the recommendations of the British Standard1, this report includes the 
necessary information to support a planning application. It demonstrates that the 
impact, both direct and indirect, of the proposed development within the site, has 
been assessed and where appropriate, mitigation and tree protection proposed.  


2.3. The implementation of the protection methods recommended within this report are 
critical for ensuring the retained trees are successfully protected through the 
construction process and must be implemented prior to any work on site.  


2.4. This assessment is based upon the supplied layout drawing, ref: A14009 AL(2-)07 
Rev B and site survey, ref: 19510 supplied by Midland Surveys Ltd. 


2.5. The controlling authority is Reading Borough Council, Planning, Bridge Street, Civic 
Offices, Reading, RG1 2LU. 


2.6. This assessment considers the impact of the development on the constraints posed 
by the retained trees (both beneath ground: the root protection area (RPA), and above 
ground: the canopy).  


2.7. Direct impact from development comes in six main forms: 1) Surface installation 
within RPAs, 2) Root loss from excavation for foundations, drainage and other utilities 
within RPAs, 3) Soil stripping, removal and level changes within RPAs, 4) Excessive 
access facilitation pruning to retained trees, 5) Soil compaction from storage and 
vehicle movements within RPAs, 6) Soil contamination. 


2.8. Indirect impact can come from changes to the site hydrology, future pressure to prune 
or fell, failure of trees exposed by removal of neighbouring trees, and other 
environmental changes which can take several years to manifest.  


2.9. The RPA for each tree represents a minimum area in m² that should be left 
undisturbed around each retained tree. This is initially represented by a circle but is 
often adjusted to account for constraints to root growth within the site (primarily 
highways and buildings). It is therefore important to ensure the protection of trees 
both above and below ground. Recommendations are provided in the British 
Standard as to the protection of existing trees before, during and after development. 
This is achieved by ensuring the tree protection plan and arboricultural method 
statement are implemented before any commencement on site.   


                                            
1 BS5837:2012 Trees in relation to design, demolition and construction- Recommendations, London: British 
Standards Institute 
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3. Scope and Method of Survey 


3.1. The survey schedule can be found at Appendix 2. 


3.2. The survey has been carried out following the recommendations of The British 
Standard and the trees are assessed objectively and without reference to any site 
layout proposals.  Categories are based on each tree’s health and condition, together 
with an assessment of its life expectancy if its surroundings were to be unchanged.   


3.3. No discussions took place between the surveyor and any other party. 


3.4. The reference numbers of surveyed trees and groups of trees are shown on the tree 
reference plan, which is appended to this report and based on the supplied survey 
drawing.  The prefix G has been used to indicate a group of trees, and H for hedges. 
Stem locations within groups may be estimated, and indicative of canopy only. 


3.5. The tree survey was carried out from ground level only, with the aid of binoculars as 
necessary, following the VTA tree assessment method2. 


3.6. Where trees are located on neighbouring land an estimated appraisal has been made 
of their quality and dimensions. All estimated dimensions are noted in the schedule 
comments. 


3.7. Where stems or branches are obscured by ivy or other materials a full assessment of 
those parts will not be possible. 


3.8. Tree heights were measured with a clinometer, or estimated in relation to those 
measured with the clinometer. If individual tree heights are of particular concern, for 
example in shading calculations, then they are measured using a clinometer.   


3.9. Trunk diameters were measured or, where inaccessible, estimated.  Single stemmed 
trees are measured at 1.5m above ground level.  


3.10. Tree canopies, where markedly asymmetrical, were measured (or estimated by 
pacing) in four directions using a laser measure.  Symmetrical canopies are 
measured in one direction only, with dimensions in the remaining directions assumed 
to be similar.  For the canopies of groups of trees, the maximum radius for each 
compass point is measured (more complicated groups will have further notes taken 
and an accurate representation will be shown on the plan).  


 


  


                                            
2 Mattheck, C. & Breloer, H., 1998. The Body Language of Trees: A Handbook for Failure Analysis. 
London:H.M.S.O. 
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4. Trees and Site Overview 


4.1. For individual details of the subject trees see the survey at appendix 2. 


4.2. The site is a residential property set in an informal garden. The area surveyed can be 
seen ringed in blue on the aerial photograph below: 


 


4.3. No soil assessment was carried out at the time of survey. According to 
http://magic.defra.gov.uk, the soil on site is expected to be: slightly acid, loamy and 
clayey soil with impeded drainage. 


4.4. One individual tree is category B, the off-site Horse Chestnut. Category B is for trees 
that might be included in the high category, but are downgraded because of impaired 
condition (e.g. presence of significant though remediable defects, including 
unsympathetic past management and minor storm damage). 


4.5. There are three individual trees that are category C. Either due to their low inherent 
value due to low overall physiological vigour, or structural faults, or their diameter is 
less than 150mm at 1.5m above ground level.  


4.6. In terms of the category C trees and groups of trees, the boundary vegetation has 
landscape value as group features and are a constraint to any development of the 
site notwithstanding their individual category. The individual trees making up groups 
are in most cases less than 150mm in diameter. They are therefore category C in 
accordance with BS5837:2012. However the group value of the trees should be 
recognised in terms of their wider landscape significance. 







Arboricultural Impact Assessment for the site at 99 St Peter’s Avenue, Caversham, RG4 7DP 
For Boyes Developments 


 


 
ACD Arboriculture, Courtyard House, Mill Lane, Godalming, Surrey, GU71EY Page | 7 
t:01483 425714 e: mail@acdarb.co.uk 


4.7. T3 is dead and is therefore category U. 


4.8. The below ground constraints posed by the trees are represented by Root Protection 
Areas (RPAs) and shown on the Tree Reference Plan. The RPA of a tree is calculated 
as advised by the British Standard. For a tree growing in an apparently unconstrained 
rooting environment a circular RPA is shown. When constraints to root growth appear 
to be present the RPA is adjusted to reflect the likely root growth pattern. 


4.9. The following photograph provides a good indication of the current conditions on site: 


 
 


T1 Horse Chestnut outside property frontage. 
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5. Arboricultural Impact Assessment 


5.1. Overview of proposed development 


5.1.1. The existing house is to be demolished and replaced with two properties. 


5.2. Planning context 


5.2.1. Tree Preservation Orders/Conservation Area: There are no Tree Preservation 
Orders (TPOs) present on any trees on, or adjacent to the site, nor is the site within a 
Conservation Area.  


5.2.2. Previous planning applications and consents: There is a current planning 
application in place ref.: 150172. 


5.3. Trees proposed for removal & surgery 


5.3.1. The following trees are proposed for removal: 


 No. Name BS Cat 


T2 
Lawson Cypress 
(Chamaecyparis 
lawsoniana) 


C 


T3 Prissard Plum (Prunus 
cerasifera ‘Prissardii’) U 


T5 Norway Maple (Acer 
platanoides) C 


 


5.3.2. In relation to the conception and design of development proposals, BS5837:2012 
section 5.1.1 states: The constraints imposed by trees, both above and below ground 
should inform the site layout design, although it is recognised that the competing needs 
of development mean that trees are only one factor requiring consideration. Certain trees 
are of such importance and sensitivity as to be major constraints on development or to 
justify its substantial modification. However, care should be taken to avoid misplaced tree 
retention; attempts to retain too many or unsuitable trees on a site can result in excessive 
pressure on the trees during demolition or construction work, or post-completion demands 
for their removal.  


5.3.1. It is therefore deemed acceptable to remove the trees listed and, as part of the 
detailed landscape design for the scheme, include suitable and sustainable replacements 
as and where appropriate. This will more than mitigate any loss that may be felt from tree 
removals, by providing robust long-term tree cover in keeping with the proposal and 
surrounding properties. 


5.3.2. Of the trees listed, T3 is to be removed as good arboricultural practice regardless 
of any development. 
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5.4. Demolition & site clearance 


5.4.1. To ensure damage does not occur to trees highlighted for retention, tree 
protection fencing must be erected before ANY plant/vehicles entering site whatsoever. 
This should be subject to a pre-commencement site meeting between the developer, their 
project arboriculturist and a representative from the Local Authority.  


5.4.2. The existing hard features at the property frontage are to be removed to allow 
construction of the drive. This work must be carried out under the supervision of the 
project arboriculturist, as per the appropriate section of the method statement to ensure 
no underlying roots are damaged. Fencing must then be erected (as shown on the TPP) 
to protect the newly exposed ground. 


5.5. Construction within RPAs 


5.5.1. The construction of all buildings is proposed outside the RPAs of retained trees.  


5.6. Access and working room within RPAs 


5.6.1. Space is required for scaffold erection and working room within the RPA of T1. 
Following the recommendations of 6.2.3 of the British Standard, ground protection will be 
employed to retain the underlying soil structure and avoid detriment to roots. This must 
be installed as per the method statement, and signed off by the project arboriculturist prior 
to the start of any work. 


5.6.2. The area to be protected is on the south western side of the RPA of T1, next to 
plot 2 and can be seen on the tree protection plan. There is a hollow in this area of the 
garden that will need to be filled to allow a suitable drive way to be installed. The area 
between the house and the drive will be soft landscaping and should therefore be built up 
with good quality topsoil. This area will then need to be protected with suitable ground 
protection. Refer to method statement for methodology. 


5.7. Permanent hard surfaces within RPAs 


5.7.1. In section 7.4 of the British Standard, permanent hard surfacing within the RPAs 
of retained trees is addressed, and recommendations made.  


5.7.2. In the case of T1, the off-site Horse Chestnut, the drive for plot 1 crosses through 
its RPA on the south western side. To avoid root damage, various design criteria must be 
met, ensuring that a no-dig approach is taken, limiting the impact on the trees.  Any design 
must be approved for use by the project arboriculturist. A proposed section is appended 
to this report. 


5.7.3. The levels will need to be raised to 600mm above existing ground level. This is 
achievable by building up layers of cellular confinement system, individually installed. 
Detailed methodology is provided within the accompanying method statement. 
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5.8. Protection fencing 


5.8.1. Figure 2 of the British Standard recommends a standard fencing design for tree 
protection. This is a weld mesh panel design, mounted upon a well-braced scaffold 
framework. This is perfectly adequate for this site and all the retained trees can be suitably 
protected by its erection before any works start on site whatsoever.  


5.9. Shade and future pressure to prune 


5.9.1. The resulting proposed layout is both sustainable and results in juxtapositions 
between trees and buildings which will not bring future requests for excessive pruning 
and/or tree removal.  


5.10. Services 


5.10.1. Full details of the service and utility provisions for the site remain to be finalised. 
However, there is adequate space for utility trenches to access the site whilst avoiding 
RPAs and exclusion zones.   


5.10.2. It is fundamental to tree protection that infrastructure design is sensitively 
approached, as trenching close to trees may damage roots and affect tree health and 
stability. Details of services have not been provided at the time of writing. The Tree 
Protection Plan, showing the constraints posed by retained trees will be passed to the 
infrastructure engineers to inform their design, ensuring that all services avoid areas of 
potential conflict. As per Figure 1 of the British Standard, once further details become 
available as part of the detailed/technical design for the site, the TPP and AMS may need 
to be revised to incorporate service details for inclusion in the tender documentation. 
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6. Arboricultural Method Statement 


TO BE READ IN CONJUNCTION WITH THE APPENDED TREE 
PROTECTION PLAN REF: PRI19866-03 


6.1. Phasing of operations & site supervision  


6.1.1. The tree protection and other arboriculturaly related works must be carried out in 
the following order: 


Phase Operation Present Notes 


P
re


li
m


in
a


ry
  1 Pre-start 


meeting 
ACD, site manager, 
groundwork, 
foreman, demolition 
foreman 


To ‘sign-off’ protection 
prior to any plant 
activity, demolition & 
groundworks on site 


2 Tree removals 
& surgery 


Tree contractor See Tree Protection 
Plan for trees to be 
removed 


D
e
m


o
li


ti
o


n
 


3 Removal of 
hard feature 
near T1 


ACD, demolition staff, 
site manager 


Supervised by project 
arboriculturist. See 
section 6.11 of method 
statement 


4 Protection 
barriers 
erected 


Fencing contractor See Tree Protection 
Plan for position and 
type of barriers 


C
o


n
s


tr
u


c
ti


o
n


 


5 No-dig drive 
installation 


ACD, groundwork 
contractor, site 
manager 


Groundwork staff to 
receive toolbox-talk 
from project 
arboriculturist. See also 
section 6.11 of method 
statement 


6 Removal of 
protection 
barriers and 
landscape 
work 


ACD, landscape 
contractor, site 
manager 


See section 6.7 of 
method statement 


6.1.2. Supervision is required should any unplanned access and/or work be required in 
the construction exclusion zone.  


6.1.3. Supervision will require the arboriculturist to be present throughout the task, to 
ensure all the arboricultural objectives are met. If the task is to take a long period of time, 
provided the arboriculturist is satisfied, and after an initial ‘tool-box talk’, the supervision 
may be reduced to telephone contact between the site foreman/contractor and 
arboriculturist. 
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6.2. Construction exclusions zone 


6.2.1. Barriers and/or ground protection must be used to protect all retained trees before 
any machinery or materials are brought onto the site, and before any demolition, 
development or stripping of soil commences.  


6.2.2. Where all activity can be excluded from the RPA, vertical barriers must be erected 
to create the construction exclusion zone (CEZ). The default position of which is shown 
on the appended Tree Protection Plan. 


6.2.3.  Where, due to site constraints, construction activity cannot be fully or 
permanently excluded from all, or part of a tree’s RPA, appropriate ground protection can 
be installed. 


6.2.4.  It is the responsibility of everyone engaged in the construction process to respect 
the tree protection measures and observe the necessary precautions within and adjacent 
to them. 


6.2.5. Inside the exclusion zone, the following shall apply: 


 No mechanical excavation whatsoever. 
 No excavation by any other means without arboricultural site supervision. 
 No hand digging without a written method statement having first been approved by 


the project arboriculturist. 
 No lowering of levels for any purpose (except removal of grass sward using hand 


tools). 
 No storage of plant or materials. 
 No storage or handling of any chemical including cement washings. 
 No vehicular access. 
 No fire lighting. 


6.2.6. In addition to the above, further precautions are necessary adjacent to trees: 


 No substances injurious to tree health, including fuels, oil, bitumen, cement 
(including cement washings), builders sand, concrete mixing and other chemicals 
shall be stored or used within or directly adjacent to the protection area of retained 
trees. 


 No fire shall be lit such that flames come within 5m of tree foliage. 
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6.3. Tree protection barriers 


6.3.1. The construction exclusion zone will be protected as per the appended tree 
protection plan that shows the default alignment of the tree protection barriers, to be 
installed prior to any of the following taking place: 


 Archaeology 
 Demolition 
 Plant and material delivery 
 Soil stripping 
 Utility installation 
 Construction works 
 Landscaping 


6.3.2. Stages for installation of barriers: 


1) Hand clearance of any vegetation to allow clear working access. 


2) Setting out of node points  


3) Barriers erected 


4) Site meeting with project arboriculturist to ‘sign-off’ tree protection fencing. 


5) Site accessible to demolition/construction traffic 


6.3.3. Once erected, all barriers will be regarded as sacrosanct, and will not be removed 
or altered without prior recommendation by the project arboriculturist and approval of the 
local planning authority.  


6.3.4. The default barrier construction is suitable for areas of high intensity 
development, and shall comprise of interlocking weld-mesh panels, well braced to resist 
impacts by attachment to a scaffold framework that is set firmly into the ground. A detailed 
specification can be found on the TPP. 


6.3.5. The images below are alternative barrier designs that have been successfully 
used on site and that ACD are happy to support if a variation from the default style is 
required. If such a variation is necessary, the approval of the project arboriculturist will be 
obtained prior to any implementation on site. 


6.3.6. Once barriers and/or ground protection have protected the exclusion zone, 
construction work can commence.  


6.3.7. All weather notices should be erected on the barriers (for example see figure 
below). 
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 Tree protection sign (download from www.acdarb.co.uk) 


 


 
Weld-mesh panels on scaffold uprights 



http://www.acdarb.co.uk/
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Weld-mesh panels on wooden posts 


 


 
Chain-link on angle-iron uprights 
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6.4. Ground protection 


6.4.1. Ground protection is to be installed in the location shown on TPP. It must be 
capable of supporting the expected loads and avoiding rutting, compaction and damage 
to the soil: as advised in section 6.2.3 of the British Standard. 


6.4.2. Stages for ground protection installation: 


1) No plant machinery to be used in the area of ground protection for whatever 
reason 


2) Discuss procedure with project arboriculturist 
3) Dismantle primary TPF and re-erect in secondary location as shown on TPP. 
4) Any shrubs, saplings or trees to be removed, are to be cut, or ground out to just 


below ground level rather than grubbed or winched out, which can damage roots 
of retained trees. 


5) Lay woven geotextile over existing ground surface by hand 
6) Cover the area with compressible layer, woodchip for example, using hand tools 


only 
7) Cover compressible layer with side butting scaffold boards or plywood boards 
8) Confirm surface is acceptable for use with project arboriculturist 
9) Area ready for construction access 


6.4.3. Any scaffolding required within the area will be erected with the uprights placed 
on spreader boards. 


6.4.4. The boarding will be left in place until the construction works are finished. 


6.4.5. A single thickness of boarding laid on the soil surface will provide sufficient 
protection for pedestrian loads. However, for wheeled or tracked construction traffic 
movements within the RPA, ground protection will involve the use of temporary cellular 
confinement systems, reinforced concrete slabs or track-board systems details of which 
are to be specified by the project engineer and approved for use by the project 
arboriculturist and local authority before construction commences. 


6.4.6. Track-boards can be sourced from Trakmats Europe Ltd, 0845 6435388, www. 
trakmatseurope.com, or groundguards.com 


6.4.7. There is to be no-excavation within ground protection area whatsoever. This 
includes installation of services and associated utilities. 
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Scaffold board pedestrian ground protection 


 
Vehicular ground protection trackway 
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6.5. Site storage, parking, welfare facilities, etc. 


6.5.1. The site will require provision for; site storage, contractor parking, welfare 
facilities, temporary services/drainage, material drop off points, etc.  


6.5.2. It is acceptable to place site cabins and walkways within the CEZ provided they 
are installed sensitively: 


 Cabins must be placed on sleepers (or similar) to spread the load, avoiding point 
loading and associated soil compaction.  


 The delivery of cabins should ensure that any unloading via ‘hi-ab’ crane can be 
carried out without impact on the crowns of retained trees. 


 Walkways, if required, should be installed as per the ground protection 
specification. 


 Any utilities for site compounds must be run above ground. For example, WC foul 
pipes/drainage and temporary electrical connections. 


6.5.3. It is imperative that if cabins and walkways are installed, that fencing is erected 
to limit access to the protected areas. If amendments are made, the project arboriculturist 
should sign off the proposals prior to their implementation.  


6.5.4. Contractor parking and storage areas should be sited outside the CEZ. 


6.6. Tree surgery and removal 


6.6.1. All trees to be removed are indicated on the TPP. 


6.6.2. If any further surgery work is proposed, details will be submitted to, and approved 
by, the council, before being carried out. 


6.6.3. All work will be carried out in accordance with BS39983 industry best practice and 
in line with any works already agreed with the council. 


6.6.4. The tree surgeon shall ideally be chosen from The Arboricultural Association's 
Approved Contractor list. All work shall be undertaken at the appropriate time and with 
the consent and approval of the site agent.  


6.6.5. The statutory protection 4  5  will be adhered to. If further advice is required, 
particularly if bats are discovered during tree work, it will be obtained from Natural 
England or other competent persons and recommendations adhered to. 


                                            
3 BS3998:2010- Recommendations for Tree Work. London: British Standards Institute 
4 Wildlife and Countryside Act. (1981) London: HMSO. 
5 Countryside and Rights of Way Act. (2000) London: HMSO. 
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6.6.6. The stumps of any trees removed from within the Construction Exclusion Zone 
or the RPAs of retained trees will be either cut flush to ground level and left in situ or 
ground out using a stump grinder. They will not be winched out. 


6.6.7. All operations shall be carefully carried out to avoid damage to the trees being 
treated or neighbouring trees. No trees to be retained shall be used for anchorage or 
winching purposes. 


6.7. Soft landscaping  


6.7.1. All landscaping and associated ground preparation within exclusion zones will be 
carried out sensitively to ensure root damage is mitigated as much as is practicable. At 
no time is any heavy plant to be used within any protected area. Removal of existing 
vegetation will be carried out by hand. Turf may be removed using a mechanical turf 
stripper or with hand tools.  


Turfing 


6.7.2. Stages for turfing gardens and open spaces: 


1) No plant/machinery to be used in the area for whatever reason. 
2) Remove TPF to allow access to area.  
3) Re-erect TPF to secondary location (if required and shown on plan). 
4) Do not reduce any high spots or excavate in any way. 
5) Existing poor quality turf may be removed with a turf stripper. 
6) Use good quality top-soil to level any low-lying areas and hollows, and provide a 


fine tilth to lay turf on. This imported soil must not result in a level increase of more 
than 100mm in any area.  


7) Import turves by hand in wheelbarrow. 
8) Lay turves. 


 
Planting 


6.7.3. Should the soil be compacted or have a poor structure that may hinder the 
development of any new planting, soil decompaction techniques may be used upon 
consultation with the project arboriculturist. 


6.7.4. Stages for planting within tree protection areas: 


1) No plant machinery to be used in the area for whatever reason. 
2) Remove TPF to allow access to area.  
3) Re-erect TPF to secondary location (if required and shown on plan). 
4) Remove existing vegetation by hand, turf may be removed using a mechanical turf 


stripper. 
5) Do not reduce any high spots or excavate in any way. 
6) Import good quality top-soil by hand (with wheelbarrow) into area. 
7) Level to a depth of no more than 100mm with hand tools. 
8) Dig individual planting pits for each plant by hand (including hedging which must 


not be trench planted). 
9) Any mulch should also be imported and spread by hand. 
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6.7.5. No works will be carried out within any protected areas if the soil moisture is of a 
level likely to allow compaction to occur. 


6.8. Installation of underground services 


6.8.1. Mechanical trenching for the installation of underground apparatus and drainage 
severs any roots present and can change the local soil hydrology in a way that adversely 
affects the health of the tree. For this reason, particular care should be taken in the routing 
and methods of installation of all underground apparatus. Wherever possible, apparatus 
should be routed outside RPAs. Where this is not possible, it is preferable to keep 
apparatus together in common ducts. Inspection chambers should be sited outside the 
RPA. 


6.8.2. Where underground apparatus is to pass within the RPA, detailed plans showing 
the proposed routeing should be drawn up in conjunction with the project arboriculturist. 
In such cases, trenchless insertion methods should be used: Microtunnelling, Surface-
launched directional drilling, Pipe ramming or Impact moling (see BS5837:2012 Table 3), 
with entry and retrieval pits being sited outside the RPA. Provided that roots can be 
retained and protected, excavation using hand-held tools might be acceptable for shallow 
service runs. If this is case, the following methodology must be followed: 


6.8.3. Stages for installing services by hand within tree protection areas: 


No plant machinery to be used in the area for whatever reason 
 


1) Contact project arboriculturist to hold pre-start site meeting and ‘toolbox’ talk 
before starting work. 


2) Remove just enough tree protection fencing to allow access to area and facilitate 
trenching. 


3) Remove any surface vegetation or existing hard surfaces using hand tools. 
4) Using and air-pick excavate the trench, keeping to minimum dimensions required. 
5) Roots occurring in clumps of 25 mm diameter and over are encountered they will 


be retained, and kept damp by covering with hessian (re-wetted as required). If 
required, these should be severed only following consultation with an 
arboriculturist; as such roots might be essential to the tree’s health and stability. 


6) Feed in services. 
7) Back fill trench with 200-300mm depth of excavated soil, or a mixture of excavated 


and imported top-soil to BS3882 (BSI, 2007), firming down with heels. 
8) Repeat step 7 until trench is filled. 
9) Re-erect tree protection fencing as per approved plan. 


6.8.4. The method of excavation above, for trenching within RPAs, is using air 
excavation. This tool utilises compressed air to remove soil from around tree roots 
causing minimal damage and can be run off a typical site compressor. ACD can provide 
details of contractors supplying air excavation services if required. 


6.8.5. Alternatively trenchless technology, such as thrust boring can be used in some 
instances and is particularly effective as it can pass directly under the tree, at a depth 
which is likely to avoid almost all impact on roots of the subject tree. As no access/thrust 
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pits will be located within the RPAs of the subject trees, the need for arboricultural 
supervision is limited. 


6.8.6. Reference can be made to NJUG Vol 46 for guidance, but any approach must be 
approved by the project arboriculturist and brought to the attention of the local authority 
tree officer. 


6.9. Demolition close to trees 


6.9.1. All TPF to be installed as per approved Tree Protection Plan prior to any plant 
arriving on site. 


6.9.2. Sensitive demolition will occur under supervision from the project arboriculturist 


6.9.3. Stages for demolition within tree protection areas: 


1) No plant machinery to be sited on any exposed rooting area 
2) Dismantle any fencing to allow work to proceed 
3) Buildings to be folded in on themselves 
4) Removal debris by hand or with plant machinery not located on any exposed 


rooting area. 
5) Floor to be broken up with had held breaker and pieces removed by hand. Slab 


floor can be lifted carefully by machinery if appropriate 
6) Underlying ground levels to be retained. No excavation to occur 
7) Any exposed roots and surrounding newly exposed areas to be covered with up to 


100mm of topsoil, from elsewhere on site, or imported top-soil to BS38827. Soil 
may be placed in area by plant but must be spread by hand. 


8) Tree protection fencing to be erected in final position as shown on plan 


6.9.4. No reduction in levels of the underlying soil surface will occur.  


6.9.5. At no point are any heavy machinery permitted within the RPA. 


6.9.6. Contamination of the soil by fuel and lubricant leaks must be avoided at all cost. 
If such a situation arises the project arboriculturist must be notified to assess the situation 
and prescribe remedial measures. 


  


                                            
6 National Joint Utilities Group. (2010). Volume 4: NJUG Guidelines For The Planning, Installation And 
Maintenance Of Utility Apparatus In Proximity To Trees (Issue 2) – Operatives Handbook. NJUG. 
7 BS3882:2007- Specification for topsoil and requirements for use. London: British Standards Institute. 
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6.10. Installation of no-dig surface  


6.10.1. To ensure that tree roots, within the ground under this proposed surface, continue 
to survive during and after construction a cellular system such a CellWeb8 of 75-200mm 
depth is to be used.  


 


 No-dig cross-section 


6.10.2. Stages for Installation of the cellular confinement surface:  


1) Contact project arboriculturist to hold pre-start site meeting and ‘toolbox’ talk before 
starting work 


2) Dismantle TPF and re-erect in secondary location as shown on TPP 


3) Remove existing vegetation by using a specific herbicide (as advised by a specialist) 
or manual removal with hand tools only. Agreed removal of shrubs, saplings or 
trees, within the protected areas of retained trees are to be cut, or ground out to just 
below ground level rather than grubbed or winched out, which can damage roots of 
retained trees.  


4) Retain all original ground levels after vegetation removal. No excavation 
whatsoever. 


5) Remove any existing hard surfaces (paving, tarmac etc.) Hand tools should be used 
if possible. If machinery is required for this operation, it must be used only on 
existing surfaces or outside the protection areas and tree canopies (approval from 
project arboriculturist must be sought before using machinery). The sub base of 


                                            
8 Geosynthetics Ltd, 01455 617139, www,geosyn.co.uk 
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existing surfaces or foundations should be left in situ where possible to avoid 
unnecessary root disturbance and provide a base for the new surface.  


6) Install a non-woven Geotextile (such as TreeTex T300) directly over soil grade level 
(levelled where necessary, by non-compacted washed sand) and fix in place. 


7) Lay the cellular system over the Geotextile, which is secured open under tension 
during the infill process with steel staples or wooden pegs.  


8) Install kerbs and edgings directly on top of existing soil grade level. For light 
structures, a treated peg and board may be acceptable. For more substantial 
structures, railway sleepers, haunched concrete with road pins, drilled kerbstones, 
gabions or cast in situ kerbs will be appropriate.  


9) Fill the cellular system ensuring any machinery works only on already filled areas. 
Typical infill consists of no fines angular granular material 20-40mm, which will 
remain un-compacted. 


10) Cover with a non-woven Geotextile (such as TreeTex T300). 


11) Install porous wearing surface. 


 Small Block Paving 
 Washed Gravel 
 Porous Asphalt 


6.10.3. Any variation to the above specification must meet the following design criteria 
for low-invasive surfaces to provide the conditions for continued tree survival and growth: 


 Maintain oxygen diffusion through new surface to rooting area (5-12% by volume9) 
 Maintain sufficient passage of water to the rooting area (12-40% by volume10) 
 Avoid compaction by maintaining a soil structure sufficient to sustain root growth 


(soil bulk density below 1.4g/cc11). 


6.10.4. Site analysis of the soil type and its structural characteristics will be required prior 
to determining the specific depth of products to be adopted for example, footpaths 
normally require a depth of 75mm and, 100mm to 200mm depths are used for residential 
driveways, while greater depths may be required for the passage of heavier traffic such 
as for construction access and delivery vehicles.  


6.10.5. If ground levels are to be raised more than 150mm this should be achieved by 
the use of a granular material, which does not inhibit vertical gaseous diffusion. For 
example: no-fines gravel, washed aggregate, structural soil (min. 20% sand content) or 
cobbles. 


  


                                            
9 Smith, R. J. (2006). Tree Roots in the Built Environment. HSO 
10 Coder, D. K. (2000). Tree Root Growth Requirements. University of Georgia 
11 Harris, C. M. (2004). Arboriculture, Tree Management of Shade Trees and Vines.  
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6.11. Hard landscape removal 


6.11.1. No hard landscape removal within RPAs will occur without arboricultural 
supervision. 


6.11.2. Stages for hard surface removal within tree protection areas: 


1) No plant machinery to be sited on any exposed rooting area 
2) Contact project arboriculturist to hold pre-start site meeting and ‘toolbox’ talk 


before starting work 
3) Dismantle fencing as required to access area 
4) Plant machinery to run only on existing hard surfaces with consent from 


arboriculturist 
5) Surfaces are to be removed by hand (paving etc.) 
6) Where any sub base is not likely to contain roots, and only on approval from 


project arboriculturist, it may also be carefully removed. 
7) Underlying ground levels to be retained. No excavation to occur 
8) Any exposed roots  and surrounding newly exposed areas to be covered with up 


to 100mm of topsoil, from elsewhere on site, or imported top-soil to BS388212  Soil 
may be placed in area by plant but must be spread by hand. 


9) Tree protection fencing to be erected in final position as shown on plan 


6.11.3. If the area around the retained trees is to be left following the removal of the 
existing hard surface, before a new hard surface is laid or soft landscaping implemented, 
then the line of protective fencing MUST be correctly re-established immediately the hard 
surface removal work has been completed. 


6.11.4. If, for whatever reason there is a delay before the area is left exposed prior to 
awaiting a new surface, then a temporary surface must be implemented or the area 
fenced off. 


  


                                            
12 BS3882:2007- Specification for topsoil and requirements for use. London: British Standards Institute. 
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6.12. Installation of boundary fencing within protected areas 


6.12.1. Stages for installing wooden fence posts: 


No plant machinery to be used in the area for whatever reason 


1) Contact project arboriculturist to hold pre-start site meeting and ‘toolbox’ talk 
before starting work. 


2) Remove TPF to allow access to area.  
3) Dig postholes using hand tools, avoiding damage to the protective bark covering 


larger roots. Roots smaller than 25mm diameter may be pruned back using either 
secateurs or a hand saw, leaving a clean cut.  


4) Damage or severance of roots above 25mm diameter must be avoided. If roots of 
this size are discovered, the hole should be relocated. If there are a large number 
of such roots it may be necessary to relocate the hole by half a fence panels 
length and adjust the fence panels accordingly. 


5) Line hole with non-porous lining, for example durable polythene bag. 
6) Insert post and fill post-hole with concrete to just below ground level. 
7) Trim polythene to ground level and fill with clean topsoil. 
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Appendix 1: Tree Categories Explained 


BS5837:2012 Table 1 -Cascade chart for tree quality assessment     


Category and definition  Criteria (including subcategories where appropriate)  
    


Trees unsuitable for retention (see Note)          
Category U  *Trees that have a serious, irremediable, structural defect, such that their early loss is 


expected due to collapse, including those that will become unviable after removal of other 
category U trees (e.g. where, for whatever reason, the loss of companion shelter cannot be 
mitigated by pruning)  
*Trees that are dead or are showing signs of significant, immediate, and irreversible overall 
decline  
*Trees infected with pathogens of significance to the health and/or safety of other trees 
nearby, or very low quality trees suppressing adjacent trees of better quality  


Those in such a condition 
that they cannot realistically 
be retained as living trees in 
the context of the current 
land use for longer than 10 
years 


  
NOTE Category U trees can have existing or potential conservation value which it might be 
desirable to preserve; see 4.5.7.  


  


1 Mainly arboricultural 
qualities  


  2 Mainly landscape qualities    3 Mainly cultural 
values, including 
conservation  


Trees to be considered for retention          


Category A  
Trees that are particularly 
good examples of their 
species, especially if rare 
or unusual; or those that 
are essential components 
of groups or formal or 
semi-formal arboricultural 
features (e.g. the 
dominant and/or principal 
trees within an avenue)  


 
Trees, groups or woodlands of 
particular visual importance as 
arboricultural and/or landscape 
features  


 
Trees, groups or 
woodlands of 
significant 
conservation, 
historical, 
commemorative or 
other value (e.g. 
veteran trees or 
wood-pasture)  


Trees of high quality with 
an estimated remaining life 
expectancy of at least 40 
years 


  


  


  


Category B  
Trees that might be 
included in category A, 
but are downgraded 
because of impaired 
condition (e.g. presence 
of significant though 
remediable defects, 
including unsympathetic 
past management and 
storm damage), such that 
they are unlikely to be 
suitable for retention for 
beyond 40 years; or trees 
lacking the special quality 
necessary to merit the 
category A designation  


  
Trees present in numbers, usually 
growing as groups or woodlands, 
such that they attract a higher 
collective rating than they might as 
individuals; or trees occurring as 
collectives but situated so as to 
make little visual contribution to the 
wider locality  


  
Trees with material 
conservation or 
other cultural value  Trees of moderate quality 


with an estimated remaining 
life expectancy of at least 
20 years 


  


  


Category C  
Unremarkable trees of 
very limited merit or such 
impaired condition that 
they do not qualify in 
higher categories  


  
Trees present in groups or 
woodlands, but without this 
conferring on them significantly 
greater collective landscape value; 
and/or trees offering low or only 
temporary/transient landscape 
benefits  


  
Trees with no 
material 
conservation or 
other cultural value  Trees of low quality with 


an estimated remaining life 
expectancy of at least 10 
years, or young trees with a 
stem diameter below 
150mm   
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CLIENT: Boyes Developments           SURVEYOR: C Price TechArborA 
SITE: 99 St Peter’s Avenue, Caversham, RG4 7DP  
DATE: April 2015              TAGGED?  No 


 


Notes:  Dia (stems): trunk diameter in mm at 1.5m above ground level (number of stems) | HT (crown): Tree height (crown clearance) | Life stage:  Y: Young (obviously planted 
within the last three years (unless as a heavy or extra-heavy standard)). SM: Semi mature (recently planted and yet to attain mature stature; up to 25% of attainable age.). EM: Early mature (almost 
full height, crown still developing and seed bearing; up to 50% of attainable age.). M: Mature (full height, crown spread, seed bearing; over 50% of attainable age.). OM: Over mature (full size, die-
back, small leaf size, poor growth extension.).| FSB: First significant branch (& compass bearing) | ERC:  Expected remaining contribution in years- <10, 10+, 20+, 40+ (assuming 
that there will be no physical changes to its immediate environment.| BS Category:  Refer to appendix 1 of this report or BS5837:2012 Table 1 for detailed descriptions. 
       Page | 28 


Tree Survey Schedule 


No. Name 
Ht 


(crown) 
Dia 


(stems) 
Canopy spread  


N | E | S | W 
Life 


stage 
ERC 


Comments & preliminary 
recommendations 


BS 
Cat 


T1 
Horse Chestnut 
(Aesculus 
hippocastanum) 


17 (3) 680 (1) 7 8 7 7 M 20+ Street tree with good landscape value. B2 


T2 
Lawson Cypress 
(Chamaecyparis 
lawsoniana) 


11 (2) 260 (1) 2 2 2 2 EM 10+ Tree of little quality or value. C2 


T3 Cherry Plum (Prunus 
cerasifera) 6 (2) 600 (1) 3 3 3 3 OM <10 Dead. U 


T4 
Sawara Cypress 
(Chamaecyparis 
pisifera) 


10 (1) 260 (1) 2 2 2 2 SM 10+ Limited quality and value. C2 


T5 Norway Maple (Acer 
platanoides) 4 (2) 100 (1) 1 1 1 1 SM 10+ Tree has been 'topped'. Little quality and value. C1 


H1 


Lawson 
Cypress,Beech,Cherry 
Laurel 
(Chamaecyparis 
lawsoniana,Fagus 
sylvatica,Prunus 
laurocerasus) 


 2 (0)  - - - - - EM - Effective boundary screen. C2 


H2 Cherry Laurel (Prunus 
laurocerasus)  2 (0)  - - - - - SM - Effective boundary screen. C2 
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Appendix 3: Tree Protection Plan 
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For pedestrian movements  only, a single thickness of scaffold boards should be placed either
on top of a driven scaffold frame, so as to form a suspended walkway, or on top of a
compression-resistant layer (e.g. 100 mm depth of woodchip), laid onto a geotextile.


For pedestrian operated plant up to a gross weight of 2 t, proprietary, inter-linked ground
protection boards should be placed on top of a compression-resistant  layer (e.g. 150 mm depth
of woodchip), laid onto a geotextile.


For wheeled or tracked construction traffic exceeding 2 t gross weight, an alternative system
(e.g. pre-cast reinforced concrete slabs) should be employed to an engineering specification
designed in conjunction with arboricultural advice to accommodate the likely loading to which it
will be subjected.


RESTRICTIONS WITHIN TREE PROTECTION AREAS


Inside the exclusion area of the fencing, the following shall apply:
• No mechanical excavation  whatsoever
• No excavation by any other means without arboricultural site supervision
• No hand digging without a written method statement having first been approved by


the project arboriculturist.
• No lowering of levels for any purpose (except removal of grass sward using hand


tools)
• No storage of plant or materials
• No storage or handling of any chemical including cement washings
• No vehicular access
• No fire lighting


In addition to the above, further precautions are necessary adjacent to trees:
• No substances injurious to tree health, including fuels, oil, bitumen, cement


(including cement washings), builders sand, concrete mixing and other chemicals
shall be stored or used within or directly adjacent to the protection areas of retained
trees


• No fire shall be lit such that flames come within 5m of tree foliage.


PHASING & SUPERVISION OF DEVELOPMENT


Before any work starts on site, the tree protection measures shown on this plan are to be


installed and a pre-start site meeting with the project arboriculturist, groundwork


contractors, site manager and LPA arboricultural officer/landscape officer held.


Additional site supervision and input from the project arboriculturist is to occur:


1. During the removal of existing hard features within RPA of T1
2. During the no-dig drive surfacing


Supervision is also required should any unplanned access and/or work be required in the
construction exclusion zone


TREE TO BE REMOVED


ROOT PROTECTION AREA (RPA) FOR RETAINED TREES


A CATEGORY TREE


B CATEGORY TREE


C CATEGORY TREE


U CATEGORY TREE


INDICATIVE SERVICE ROUTE AVOIDING PROTECTION AREAS


TEMPORARY FENCING


The fencing is used to protect areas of special detail. It is to be installed
with the main tree protection fence and is only to be removed when the
detail is installed as per the method statement & under the supervision of
the project arboriculturist. It shall be weld-mesh panels on boots, secured
to the ground with road pins (or similar).


NO-DIG SURFACE


Cellular confinement system (CCS) to be used to create this area of hard
surface, above the existing ground level. Topsoil to be retained. Depth of
CCS to be 50-75mm for pedestrian surfaces and 100-200 for vehicular
surfaces. Surface to be porous to approved details and specifications. To
be installed under arboricultural  supervision. All specifications subject


to engineering design .


WHY TREE PROTECTION IS NEEDED


1) Soil compaction kills roots- caused by plant movement and storage
of materials within protected areas .


2) Trenching severs roots- many small roots grow within the top
600mm of soil. Even the removal of the top 200mm can cause damage.
3) Soil pollution kills roots-  Dripping fuel storage or cement washings
can contaminate the soil resulting in root death.
4) Raising & lowering levels kills roots-  the soil used to increase
levels can compact the underlying soil (see point 1). Lowering levels will
remove roots causing damage to the tree.
5) Bark and branch damage- bark removal and branch damage can
allow disease and fungi into the tree.
The impact of any of the above can take years to show- trees can
have huge reserves of food and water.


EXISTING SITE LAYOUT


PROPOSED SITE LAYOUT


Construction Exclusion Zone


Root protection areas (RPA) of retained trees within which all construction
activity is restricted.


All trees that are being retained on site must be protected by barriers
and/or ground protection  before any materials or machinery are brought
onto the site, and before any demolition, development or stripping of soil
commences. Where all activity can be excluded from the RPA, vertical
barriers must be erected to create a construction exclusion zone. Where,
due to site constraints, construction activity cannot be fully or permanently
excluded in this manner from all or part of a tree’s RPA, appropriate
ground protection can be installed.


Default position for the tree protection barriers.


BS5837:2012 Figure 2- barrier specification


Ground Protection


Where the set-back of the tree protection barrier would expose unmade
ground to construction damage, new temporary ground protection should
be installed as part of the implementation of physical tree protection
measures prior to work starting on site.


Examples of alternative barrier designs can be found in the method statement. Should an
alternative design be more viable and appropriate, it must be agreed with the project
arboriculturist before its implementation.


1 Standard scaffold poles
2 Heavy gauge 2m tall galvanized tube and weld mesh infill panels
3 Panels secured to uprights and cross-members with wire ties
4 Ground level
5 Uprights driven into the ground until secure (minimum depth 0.6m)
6 Standard scaffold clamps 5


4


6


3


1


2 m


3 m


4


4


4


6


6


6


Original ground
level level


Peg and board edging


Top soil to
BS3882:2007


Depressions
and soft spots in
formation to be
filled with sharp
sand to levels
required


Porous surface to finish


TreeTex T300 non-woven geotextile or
similar approved laid over formation


CCS/Cellular
confinement system
(Geosynthetics CellWeb
or similar approved)


Cells to be filled with 20-40mm clean graded angular
stone to manufacturers details and specifications


TreeTex T300 geotextile or similar laid over CellWeb







 


 


Appendix 4: Proposed Section for Driveway 
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