## Sheet1
WATERFRONT SQUARE - CONSULTATION COMMENTS TRACKER
Date: | 2024-12-19
Rep. No. | Statutory / Public | Response From | Commentary | Response Topic | Consultant/Party Responsible | Date Requested | Date Due | Notes
9 | Statutory | Transport | Review the cycle parking proposals to ensure that the 136 spaces can be accommodated as proposed | Transport | Stantec/Assael | 2024-11-12 | 2024-12-02 | Submitted 19/12/2024 - See drawing number 332610561-STN-HGN-XX-DR-H-0019
13 | Statutory | Access Officer | How will terraced seating be made safe for the blind/visually impaired? | Accessibility | Assael Exteriors | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | How will tactile markings be demarcated and also safe for wheelchair/scooter users? | Accessibility | Assael Exteriors | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Will the podium deck be accessible to wheelchair users? | Accessibility | Assael/Assael Exteriors | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | How will disabled users deal with their refuse and bulky waste? | Accessibility | Stantec/Assael/Packaged | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | How will shared paths be made safer for the visually impaired, blind and those with walking difficulties? | Accessibility | Stantec | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Can an audio element to the real-time display screen in reception be provided to assist with bus/train times? | Accessibility | Packaged | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Will management have details of local specialist transport? | Accessibility | Stantec/Packaged | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Information should be in accessible formats | Accessibility | Opus/Packaged | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Management should organise inclusive events | Accessibility | Opus | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | There should be inclusive equipment in the play area | Accessibility | Assael Exteriors | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Mix of seating to be provided to meet different user needs | Accessibility | Assael Exteriors | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
13 | Statutory | Access Officer | Option of shower only for some accessible apartments | Accessibility | Opus/Packaged | 2024-11-22 | 2024-12-06 | Submitted 19/12/24 - See Response to Access Officer's comments document
15 | Statutory | Transport | Concerns regarding the placement of two new trees on Vastern Road and impacts on visibility, the cycle route and canopies overhanging the carriageway | Transport | Stantec | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See drawing number 332610561-STN-HGN-XX-DR-H-0018 and Technical Note TN005
16 | Statutory | Ecology | Bat licence required to cover mitigation works | Ecology | TEP | 2024-11-29 | 2024-12-13 | Agree to condition
16 | Statutory | Ecology | CEMP required (to be conditioned) to ensure protection of wildlife and the Thames during construction | Ecology | TEP | 2024-11-29 | 2024-12-13 | Agree to condition
16 | Statutory | Ecology | Disagreement regarding the watercourse assessment which is requested alongside an amended BNG assessment. | Ecology | TEP | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See 6th December note to RCA
16 | Statutory | Ecology | Landscaping and lighting to be secured by condition. | Ecology | TEP | 2024-11-29 | 2024-12-13 | Agree to condition
17 | Statutory | LLFA | Detail to confirm the existing discharge rate required. | Drainage | Hexa | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See Updated Drainage Statement
17 | Statutory | LLFA | Request to resend the appendices, which do not appear to have been saved correctly | Drainage | Hexa | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See Updated Drainage Statement Appendices
18 | Statutory | Natural Environment | Constraints plan does not highlight existing trees within the site, only on the river frontage | Landscape | Assael Exteriors, Assael, Hoare Lea | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See response to NE Officer's comments document
18 | Statutory | Natural Environment | Landscape character areas plan does not show private gardens (section 5 of the DAS) and is not consistent with green roof extent on p.106. | Landscape | Assael Exteriors, Assael, Hoare Lea | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see updated plan, ref: A4012E-ASA-XX-00-DR-L-0230, Rev P1
18 | Statutory | Natural Environment | The private gardens are not shown as part of residents amenity and in the landscape details they only include hedges, unlike in the DAS visuals | Landscape | Assael Exteriors | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See response to NE Officer's comments document
18 | Statutory | Natural Environment | Trees in Vastern Road are required to meet site tree policy requirements, but are dependent on LPA and Thames Water agreements. Confirmation is required prior to decision that these can be provided | Landscape | Assael Exteriors | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document
18 | Statutory | Natural Environment | Disagree that the planting on the Vastern Road frontage is significant given only two off-site trees are proposed. Unclear what is being planted on-site. Significant shrub planting, including large shrubs, is expected. Given the minimal set back it is hard to appreciate how the space available could effectively soften the extent of hard facade to Vastern Road | Landscape | Assael Exteriors | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document and Stantec Technical Note TN005
18 | Statutory | Natural Environment | Indicative landscaping on p.107 of DAS is not consistent with visuals, the latter showing a small tree on the frontage (at the centre). | Landscape | Assael Exteriors | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document and updated drawing A4012E-ASA-XX-00-DR-L-0200, Rev P1
18 | Statutory | Natural Environment | Unclear on the plan on p.118 to the actual extent of green/brown roofs. Doesn't appear consistent with other plans. | Landscape | Assael Exteriors, Hexa | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document and updated drawing A4012E-ASA-XX-00-DR-L-0230, Rev P1
18 | Statutory | Natural Environment | Some queries about tree selection and possible conflict with Ecological requirements | Landscape | Assael Exteriors, TEP | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See updated Arboricultral Statement
18 | Statutory | Natural Environment | SuDS principles indicate linked tree pits, but no detail provided in the tree pit drawings or landscape plans. Need details of soil volumes in addition. | Landscape | Assael Exteriors, Cheshire Woodlands | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments and updated Drainage Strategy drawing 700135-HEX-00-XX-RP-C-0005
18 | Statutory | Natural Environment | Landscape Proposals Ground Floor Plan does not show rain gardens, bioretention ponds or linked tree pits as it should to demonstrate landscape-led SuDS. | Landscape | Assael Exteriors, Hexa | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see updated Drainage Strategy, Table 2-1
18 | Statutory | Natural Environment | Landscape management and maintenance will not be sufficient and some of the principles included are not acceptable, e.g. extent of irrigation. | Landscape | Assael Exteriors, Hexa | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document
18 | Statutory | Natural Environment | Lack of consideration of the kitchen garden - to allow for food planting, but how will this be encouraged and maintained? Without clear organisation is will not be effectively used. | Landscape | Assael Exteriors | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document
18 | Statutory | Natural Environment | Section 5.23 of the DAS explains the ‘special’ hard landscape paviours designed to reflect the water, which I understand you are considering. It could be an opportunity to create a river based ‘picture’ or mosiac in the public square? | Landscape | Assael Exteriors, Packaged | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document
18 | Statutory | Natural Environment | For others to comment, but play strategy only considers 0-5yrs and not all. | Landscape | Assael Exteriors | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document
18 | Statutory | Natural Environment | Trees shown to be retained are largely off-site (if all the riverside trees are off-site). In reality, the applicant is retaining minimal trees on site within the red line | Landscape | Assael Exteriors
18 | Statutory | Natural Environment | 61 new trees are proposed, which would meet tree strategy aims | Landscape | Assael Exteriors
18 | Statutory | Natural Environment | A clear plan showing existing and retained service routes for utilities, alongside new service routes is required to demonstrate landscape feasibility | Landscape | Assael Exteriors, Hoare Lea | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document and Page 7 of Utilities Statement for the utility plan
18 | Statutory | Natural Environment | Considered off-site trees should be crown-lifted rather than pruned back to the site boundary | Landscape | Cheshire Woodlands | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See Updated Arboricultral Statement
18 | Statutory | Natural Environment | Concern regarding need for post-development periodic and ongoing pruning of new trees, which suggest that the building is too close and doesn't allow for future growth of new trees | Landscape | Cheshire Woodlands | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See Updated Arboricultral Statement
18 | Statutory | Natural Environment | T22, T23 and G4 are Ash trees with low likelihood of long-term survival and should not be relied upon to contribute to the landscape provision. New trees here should be considered. | Landscape | Cheshire Woodlands | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See Updated Arboricultral Statement
18 | Statutory | Natural Environment | The AIA does not include impact on retained riverside trees. Need detail to understand what is planned within RPA's and management of this - an AMS will be required. | Landscape | Cheshire Woodlands | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - See Updated Arboricultral Statement
18 | Statutory | Natural Environment | Request for clear plan showing cycle and footpath and retained trees to confirm sufficient space available. | Landscape | Assael Exteriors, Stantec | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see response to NE Officer's comments document and updated drawing A4012E-ASA-XX-00-DR-L-0230, Rev P1
19 | Statutory | Archaeology | Condition suggested | Archaeology | Opus Works, Packaged
20 | Statutory | RBC Conservation | No objection | Conservation | N/A
21 | Statutory | RBC Housing | Sets out a reiteration of Housing and Affordable Housing required in terms of policy - quantum, tenure, mix, identifying changes to make the scheme policy-compliant. | Housing | Packaged, Opus Works | 2024-12-03 | 2024-12-13 | This will largely be covered by the findings of the FVA.
22 | Statutory | ArcAero | The applicant states that they use an empirical formula based on experimental data to estimate the effects of gusts. The methodology to establish this relationship is however unclear to us. Can the applicant provide additional detail / evidence as appropriate? | Wind and Microclimate | GIA | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see WMC response to Blewburton document
22 | Statutory | ArcAero | The report suggests that access to the SW corner of the Level 8 terrace is restricted by landscaping features, and that wind speeds will be reduced by the replacement of an open railing with a solid parapet, and therefore will also eliminate the exceedances found at the area. While plausible, this is an unsupported claim. Can the applicant superimpose the extents of the inaccessible region over the results to show that the regions indeed overlap, or perform an additional simulation with the mitigations in place to demonstrate that these measures are indeed effective? | Wind and Microclimate | GIA, Assael | 374343 | 2024-12-13 | Submitted 19/12/2024 - see WMC response to Blewburton document
23 | Statutory | ArcAero | Images are provided of the proposed development in existing surrounds. Can the applicant also provide images of the existing site, so the reader can understand the additional mass and different features being introduced to the site? | Wind and Microclimate | GIA, Assael | 2024-11-29 | 2024-12-13 | Submitted 19/12/2024 - see WMC response to Blewburton document