19/02/2026

Planning Application Ref: 	PL/25/1817
Officer: 			Catrin Davies
Application Type: 		Approval of details reserved by a condition
Address: 			37 CHAPEL HILL, TILEHURST, RG31 5BT
Proposal:			Application for Approval of Details Reserved by Conditions 
3 (Materials) , 4 (Photovoltaic statement) and 5 (Construction Method Statement) of application PL/24/1244

CMS 5
The proposed work should be in accordance with the Borough’s Guidance Notes for Activities on the Public Highway. Any licenses required for the development can be obtained from the Councils website using the following link. http://www.reading.gov.uk/maintenanceandroadworks
 
· Space on site where vehicles of site operatives and visitors can be parked with details of how site operatives and visitors will be required to make use of the parking area provided.
Narrative states that parking will be provided within the site boundary and where this is not possible operatives will be instructed to park on surrounding public 
Operatives should not be parking on the public highway and alternatives should be sought.  A site plan has not been submitted illustrating the on site parking provision. 
UNSATISFACTORY
 
· Location on site for storage of plant and materials used in constructing the development.
No site plan submitted illustrating locationNo part of the public highway can be used for the storage of any plant or materials. 
UNSATISFACTORY
 
· Erection and maintenance (including removal of any graffiti or fly posters) of security hoarding around the site.
Narrative states temporary secure fencing or hoarding will be erected around the working area.  No site plan has been submitted illustrating extent and location of hoarding and gates.   Gates must not open out on to any part of the public highway.
UNSATISFACTORY
 
· Footpath closures or road closures needed during construction.
None stated.  If any road closures are required, the requirements of Section 8, of the adopted Guidance Notes for Activities on the Public Highway must be adhered to.  No part of the footpath/public highway outside the site must be used by the contractor.
SATISFACTORY
 
· Wheel washing facilities on site.
No site plan submitted illustrating wheel washing facility.   All access routes and the carriageway and footway must be regularly inspected and kept clear of dirt and debris.
UNSATISFACTORY
 
· Scheme for recycling waste resulting from the construction works.
Not for Transport to comment.
 
· Scheme for recycling waste resulting from the construction works.
Not for Transport to comment on.


N.Hussain
Transport Development Control Advisor

