## Cover Sheet
GS Property
Developments Limited
QUOTATION (Rev D) -referred in the Contract as the Contractor' Priced Schedule of work
CONVERSION OF YEOMANRY HOUSE, 131 CATSLE HILL, READING
INTO
THREE TERRACE HOUSES AND FIVE ONE BEDROOM APARTMENTS
2026-03-16
G S Property Developments Ltd
29 Little Heath Road
Tilehurst
Reading
RG31 5TY
Contact: | Paul Spokes
Tel: | 0118 9412227 & 07793 444084
Email: | paul@gs-property.co.uk

## Contents
CONTENTS
1.0 | QUOTATION SUMMARY
2.0 | BASIS OF QUOTATION
3.0 | SCHEDULE OF WORKS
APPENDIX A
Drawings and specifications used to prepare this quotation.

## 1 Exec Summary
1.0 | QUOTATION SUMMARY
Ref. | Element |  |  | Total
.01 | Demolitions & Alterations |  |  | 203402
.02 | Excavation and earthwork |  |  | 74250
.03 | In Situ Concrete |  |  | 0
.04 | Pre Cast Concrete |  |  | 0
.05 | Brickwork and Blockwork |  |  | 33995
.06 | Roofing |  |  | 39175
.07 | Woodwork |  |  | 143914
.08 | Windows and external doors |  |  | 130625
.09 | Steelwork |  |  | 5000
.10 | Metalwork |  |  | 0
.11 | Plumbing & Mechanical Engineering Installations |  |  | 267245
.12 | Electrical Installations |  |  | 90000
.13 | Floor Finishes |  |  | 29500
.14 | Wall Finishes |  |  | 81655
.15 | Ceiling Finishes |  |  | 42540
.16 | Furniture & Fittings |  |  | 121500
.17 | Painting & Decorating |  |  | 58645
.18 | External works |  |  | 232590.05
.19 | Preliminaries |  |  | 160310
| TOTAL | (Excluding VAT, Design Fees & CIL charges - see section 2 for further information) |  | 1714346.05
|  |  | COST PER Sq/ft (Exc VAT) | 219.2344 | sq/ft
|  |  | COST PER Sq/ft (ExcL EXTERNAL WORKS & VAT) | 189.4902 | sq/ft
FOR INFORMATION ONLY
Gross Floor Area |  | m2 | ft2
Basement
Ground floor
First floor
Second floor
Total |  | 726.4 | 7819.696

## 2 Basis
2.0 | BASIS OF QUOTATION
2.1 | Brief description of the Works
Conversion of Yeomanry House into three terrace houses and five one bed apartments
| Architect: |  | Colony Architects
| Structural Engineer: |  | TBS
| Warranties & Insurances: |  | TBA
2.2 | Assumptions
2.2.1 | The works will not be phased
2.2.2 | The foul water drainage will fall by gravity into a the existing mains system on site. All licenses permissions etc. for these works to be arranged and paid for by others.
2.2.3 | Temporary electricity (100 amp supply) and water supplies/services will be provided free of charge by the Employer.
2.2.4 | Electricity & water supplies are readily available on site. G S Property Developments Ltd has included provisional quantities for service trenches and ducts within the site up to the site boundary. The Employer shall arrange and pay for electricity, water (including drainage), gas, telecom supplies, services, connection and infrastructure fees/charges.
2.2.5 | The Employer shall discharge all necessary planning conditions and Building Control conditions. The Employer's designers shall advise the Employer on all design matters including planning and building control implications as a result of changes from the approved planning drawings. G S Property Developments Ltd will call out the Building Control Surveyor for any necessary key stage inspections.
2.2.6 | Fortnightly interim payments with 3% retention. Half the retention fund released on Practical Completion, issue of the Building Control Completion Certificate or occupation (whichever is the earliest) of the works and final payment including release of retention monies 6 months later.
2.2.7 | We have assumed we will not be excavating below the ground water level as no allowance has been made for dewatering
2.2.8 | A structural warranty is to be obtained and paid for by the client.
2.2.9 | Asbestos survey will be arranged and paid for pay the client - Now included
2.2.10 | Heating and hot water served by suitably sized gas boilers with electric heating to the common areas
2.3 | Exclusions
2.3.1 | Gas, water (including drainage), telecoms and electricity supplies, services, connections, service alteration and infrastructure fees/charges - to be paid by the client. - Provisional sum now included for these works
2.3.2 | Planning fees and charges including and contributions due under Section 106 and/or 278 agreements and the Community Infrastructure Levy.
2.3.3 | Building Regulation fees and charges.
2.3.4 | Party wall awards, notices, fees and charges under the Party Wall etc. Act 1996.
2.3.5 | Building Warranty & Insurance fees and charges e.g. Zurich, NHBC Buildmark or NHBC Solo, etc.
2.3.6 | Value Added Tax
2.3.7 | All design fees and charges including building regulations drawings, working drawings, structural calculations, as built drawings, survey drawings, ground investigations, hydrological reports, contamination reports, ground stability reports, environmental reports, SAP calculations, Energy Performance Certificate, and the code for sustainable homes report.
2.3.8 | Drainage build over notices.
2.3.9 | Rediverting any mains services.
2.3.10 | Removing any asbestos or other contaminated or deleterious materials - Asbestos removal now included
2.3.11 | Carpets, curtains, blind and other soft furnishings - to be supplied and fitted by the client.
2.3.12 | Soft landscaping, seeding, planting etc. - Provisional sum now included
2.3.17 | Electric entrance gate, intercom etc.
2.3.18 | Fire alarm panels - assumed linked heat and smoke detectors sufficient
2.3.19 | No allowance for CCTV survey or remedial works to the existing retained foul and surface water drains
2.3.20 | Demolition notice fees including an asbestos report - to be arranged and paid for by client. An asbestos report and approved demolition notice will be required prior to demolition
2.3.21 | All works associated with protected species such as Bats, newts, slow worms, doormice etc including any ecological surveys required /licenses needed. These costs if any to be borne by the client
2.3.22 | Any works in the basement
2.3.23 | Lightning protection system
2.2.24 | Wet rot, dry rot or timber infestation repair or treatement - Provisional sum now included
2.2.25 | Works to basement
2.2.26 | Any tranking or damp proofing works
2.2.27 | Any underpinning works
2.2.28 | Foundations deeper than 1m below existing ground fevel
2.4 | Drawings used to prepare quotation
| 2.4.1 | This quotation is based on the specification and drawings set out in Appendix A.
| 2.4.2 | Please note we have relied on the accuracy and sufficiency of the information in the designs and drawings produced by the Employer's designers.
2.5 | Provisional Sums (PS) and Prime Cost Sums (PC sums)
2.5.1 | Various provisional sums and prime cost sums have been included in this quotation. These will be adjusted accordingly when the actual costs are known with a 20% addition to cover our head office overheads and profit.
2.6 | Provisional Quantities
2.6.1 | Various provisional quantities have been included in this quotation. These provisional quantities will be adjusted accordingly when the actual quantities are known.

## 3 SofW
3.0 | SCHEDULE OF WORKS
|  | Quant. | Unit | Rate | Total | LABOUR | MATERIALS | PLANT | SUB CONTRACT | TOTAL | Check Sum
3.01 | DEMOLITIONS & ALTERATIONS
- | Asbestos refurbishment and development survey | 1 | Itm | 1400 | 1400
- | Remove asbestos found - quotation received from Stacey's £44,000 + Vat + OHP. This excludes scaffolding. Most of these costs doe to asbestos found in the external paint so all needs to be removed | 1 | Itm] | 52800 | 52800
- | Extra over for encapsulated scaffolding and additional hire | 1 | Itm | 5000 | 5000
- | Disconnection of redundant electrical services | 1 | Itm | 2745 | 2745
- | Ditto mechanical services | 1 | Itm | 2745 | 2745
- | Removal of redundant fixtures and fittings | 1 | Itm | 4950 | 4950
- | Internal demolition and alterations to unit 6 - Inc new window opening | 1 | Itm | 25950 | 25950
- | Extra over to remove staircase and make floor structure; staircase moved to all floors | 1 | Itm | 2000 | 2000
- | Ditto unit 7 | 1 | Itm | 22450 | 22450
- | Extra over to remove staircase and make floor structure; staircase moved to all floors | 1 | Itm | 3500 | 3500
- | Ditto units 1,2,3,4 & 5 | 1 | Itm | 47872 | 47872
- | Ditto Unit 8 | 1 | Itm | 24950 | 24950
- | Block up door way between play room and kitchen | 1 | Itm | 850 | 850
- | Skips associated with the above demolition and alterations | 1 | Itm | 4945 | 4945
- | Removal and disposal of external staircase | 1 | Itm | 1245 | 1245
- | Allowance to remove redundant external fixtures, fittings, paving's, landscaping etc | 1 | Itm |  | Included in External works provisional sum
203402
3.02 | NEW SIDE EXTENSION
- | New two storey side extension (PROVISIONAL SUM) | 27 | m2 | 2750 | 74250
| Section total |  |  |  | 74250
3.03 | IN SITU CONCRETE
| Section total |  |  |  | 0
3.04 | PRE CAST CONCRETE
| Section total |  |  |  | 0
3.05 | BRICKWORK & BLOCKWORK \ MASONRY
- | Allowance for render and external wall repairs including repointing (PROVISIONAL SUM) | 1 | PS | 10000 | 10000
- | Redecorate externally - render, window, doors, fascia and soffit | 1 | Itm | 21995 | 21995
- | Extra coat of paint on render as existing paint needs to be totally removed due to asbestos presence. | 1 | Itm | 2000 | 2000
| Section total |  |  |  | 33995
3.06 | ROOFING
- | Allowance for roofing repairs including works to slates, battens, etc including parapet repairs (PROVISIONAL SUM) | 1 | PS | 7500 | 7500 | 2625 | 4875 | 0 | 0 | 7500 | 0
- | Allowance for general leadwork; soakers, flashings etc repairs (PROPVISIONAL SUM) | 1 | Itm |  | Included in Prov sum above | #VALUE! | #VALUE! | 0 | 0 | #VALUE! | #VALUE!
- | Allowance for lead roof repairs following lead being stolen | 1 | Itm | 5000 | 5000
- | Thermal Rockwool type insulation between and over joists | 269 | m2 | 25 | 6725
- | Extra over for PIR insulation to units 3, 6 & 7 | 170 | m2 | 25 | 4250
- | Repair and repaint cast iron guttering (PROVISIONAL SUM) | 1 | Itm | 2500 | 2500
- | Conservation roof lights | 6 | nr | 1500 | 9000
- | Extra over to trim openings | 6 | nr | 700 | 4200
| Section total |  |  |  | 39175
3.07 | WOODWORK | [10 empty] | ,4
- | Timber floor repairs - floors to be taken up for services as the ceilings are lath and plaster. Allowance included for new boards where necessary | 1 | Itm | 23566 | 23566 | 7069.8 | 16496.2 | 0 | 0 | 23566 | 0
- | Allowance for acoustic flooring to apartments only | 265 | m2 | 85 | 22525
- | Acoustic flooring to houses - standard rockwool | 392 | m2 | 35 | Excluded assumed not required
- | Roof structure repairs including works to the dormer windows and parapets (PROVISIONAL SUM) | 1 | PS | 5000 | 5000 | 1500 | 3500 | 0 | 0 | 5000 | 0
- | Paint and repair timber fascia and soffit | 1 | Itm | 5000 | 5000 | 1250 | 3750 | 0 | 0 | 5000 | 0
- | First fix; Internal stud partitions; 50 x 100mm treated sawn softwood studding and noggins | 159 | m2 | 75 | 11925 | 5962.5 | 5962.5 | 0 | 0 | 11925 | 0
- | Unit 7 ground to first floor staircase upgrade works | 1 | Itm | 5500 | 5500
- | Uni 7 First to second floor softwood staircase | 1 | Itm | 5500 | 5500
- | Unit 6 ground to first floor softwood staircase upgrade | 1 | Itm | 5500 | 5500
- | Unit 6 first to second floor staircase | 1 | Itm | 5500 | 5500
- | Apartments ground to first floor staircase repairs | 1 | Itm | 2750 | 2750
- | Apartment first to second floor staircase | 1 | Itm | 5500 | 5500
- | Unit 8 Ground to first floor staircase | 1 | Nr | 5500 | Included in extension costs | #VALUE! | #VALUE! | 0 | 0 | #VALUE! | #VALUE!
- | Units 6, 7 & 4 MDF skirtings | 1 | Itm | 4320 | 4320
- | Repairing/matching skirtings in units 1,2,3,5 & 8 | 1 | Nr | 11450 | 11450
- | Refurbish existing doors and frames | 7 | Nr | 300 | 2100 | 1050 | 1050 | 0 | 0 | 2100 | 0
- | New internal doors and frames - PC sum of £150 to supply door and ironmongery | 43 | Nr | 445 | 19135 | 5740.5 | 13394.5 | 0 | 0 | 19135 | 0
- | Ditto double doors | 2 | pr | 895 | 1790
- | Woodwork sundries | 1 | Itm | 6853 | 6853 | 3426.5 | 3426.5 | 0 | 0 | 6853 | 0
| Section total |  |  |  | 143914
3.08 | WINDOWS & EXTERNAL DOORS
- | Allowance for external window and door repairs (No allowance for repairing window shutters to operational use) | 69 | Nr | 1165 | 80385 | 0 | 0 | 0 | 80385 | 80385 | 0
- | Allowance for secondary double glazing (PROVISIOANL SUM) | 69 | PS | 500 | 34500
- | New sash windows | 3 | Nr | 3250 | 9750
- | Extra over for new external door to units 6 & 7 (Unit 8 included in extension costs) | 2 | Nr | 2995 | 5990
| Section total |  |  |  | 130625
3.09 | STRUCTURAL STEELWORK
- | Structural steelwork - lintels included elsewhere - PROVISIONAL SUM (No design provided) | 1 | PS | 5000 | 5000 | 2000 | 3000 | 0 | 0 | 5000 | 0
| Section total |  |  |  | 5000
3.10 | METALWORK
| Section total |  |  |  | 0
3.11 | PLUMBING & MECHANICAL ENGINEERING INSTALLATIONS
- | Gas boilers to houses | 3 | Nr | 3950 | 11850 | 0 | 0 | 0 | 11850 | 11850 | 0
- | Megaflo or similar to units 6, 7 & 8 | 3 | Nr | 2995 | 8985
- | Electric boiler to flats | 5 | Nr | 3500 | 17500
- | Radiator points - column radiators or towel rails | 42 | nr | 1500 | 63000
- | Electric heaters to common areas & flats | 22 | nr | 1250 | 27500
- | Hot water points | 44 | nr | 190 | 8360 | 0 | 0 | 0 | 8360 | 8360 | 0
- | Cold water points - | 70 | nr | 190 | 13300
- | Wastes | 70 | nr | 190 | 13300
- | Soil and vent pipe including boxing | 9 | nr | 1000 | 9000
- | Allowance to supply only sanitary ware including all brassware and wet room trays, fixtures and fittings (PROVISIONAL SUM) | 1 | PS | 50000 | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0
- | Labour associated with first and second fix plumbing including fix only sanitary ware - | 1 | Itm | 32000 | 32000 | 0 | 0 | 0 | 32000 | 32000 | 0
- | Repair and paint cast iron down pipes | 1 | Itm | 2450 | 2450 | 0 | 0 | 0 | 2450 | 2450 | 0
- | Supply and fit water softener |  | Itm |  | Excluded
- | Builders work in connection with services | 8 | nr | 1250 | 10000
| Section total |  |  |  | 267245
3.12 | ELECTRICAL INSTALLATIONS
- | Electrical installation; concealed wiring; white plastic fittings PROVISIONAL SUM - to be remeasured using the following schedule of rates - | 1 | PS | 85000 | 85000
| Double socket outlet or appliance outlet |  | Nr | 95 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Shaver point |  | Nr | 126
| Supply to illuminated mirror |  | Nr | 99.75
| Towel rail heater supply |  | Nr | 105
| Oven point |  | Nr | 175
| Induction hob point |  | Nr | 175
| Extra over DSSO for integrated USB point |  | Nr | 26.25
| Pendant or batten light holder |  | Nr | 90 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Wall lights (Fittings provided by the client free of charge) |  | Nr | 100
| Light switch - max two gang |  | Nr | 89.25
| Dimmer module |  | Nr | 42
| Feature kitchen pendant lights supplied by the client |  | Nr | 157.5
| Low voltage LED down light |  | Nr | 92 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| External light supplied free issue by the client |  | Nr | 92
| PIR movement sensor |  | Nr | 92
| Kitchen wall unit LED's - LEDS supplied by others |  | Nr | 131
| TV point - final connection to aerial/satellite dish by others |  | Nr | 92 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Data - Excluding Rack works |  | Nr
| Wi-Fi booster |  | Nr | 367.5
| BT point |  | Nr | 126 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Distribution board (single phase) |  | Nr | 1100 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Extra over for 3 phase electrical board |  | Nr | 650 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Two way switching |  | Nr | 92.5 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Smoke detector |  | Nr | 175 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Heat detector |  | Nr | 175
| Carbon monoxide detector |  | Nr | 175
| Extractor fan (utility, cloak and bathroom) |  | Nr | Included elsewhere |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Kitchen extractor hood (extractor supplied by client) |  | Nr | Included elsewhere |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Earthling |  | Itm | 185 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Thermostats |  | Nr | 175 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Test and commission |  | Itm | 525 |  | 0 | 0 | 0 |  | 0 | #VALUE!
| Outside power point (PROVISIONAL SUM) |  | nr | 185
- | Garage WC water heater for basin tap) |  | nr | 675 | 0
- | Lighting to driveway including any trenching, ductwork, builders work in connection and the like (PROVISIONAL SUM) |  | PS
- | Installation of intruder alarm system - Excluding monitoring fees and any CCTV, intercom system etc |  | Itm |  |  | 0 | 0 | 0 |  | 0 | #VALUE!
- | Builders work in connection with services | 1 | Itm | 5000 | 5000
| Section total |  |  |  | 90000
3.13 | FLOOR FINISHES
- | Allowance for floor tiling (PC sum of £50/m2 to supply on tiles, adhesive, grout and trims including GSPD 20% allowance for overheads and profit) (PROVISIONAL QUANTITY) | 50 | m2 | 135 | 6750 | 5737.5 | 1012.5 | 0 | 0 | 6750 | 0
- | Extra over Detra for 'no more ply' to the upper floors (PROVISIONAL QUANTITY) | 50 | m2 | 35 | 1750
- | Extra over for laying wet room tray and tanking (Wet room tray and taking included in sanitaryware provisional sum) (PROVISIONAL QUANTITY) |  | nr | 300 | Excluded
- | Extra over for cutting in wet room trays |  | nr | 300 | Excluded
- | Supply and fit carpet and underlay (PROVISIONAL SUM) | 1 | Itm | 20000 | 20000 | 0 | 0 | 0 | 20000 | 20000 | 0
- | Entrance mat well | 1 | Nr | 1000 | 1000 | 0 | 0 | 0 | 1000 | 1000 | 0
| Section total |  |  |  | 29500
3.14 | WALL FINISHES
- | Lime plastering - including stripping walls etc making good chases etc; standard plaster works to units 6, 7 & 3 | 1 | Itm | 53450 | 53450 | 21380 | 32070 | 0 | 0 | 53450 | 0
- | Plasterboard; to studwork | 260 | m2 | 20 | 5200 | 2080 | 3120 | 0 | 0 | 5200 | 0
- | Skim coat plaster to plasterboard | 260 | m2 | 18 | 4680 | 3042 | 1638 | 0 | 0 | 4680 | 0
- | Ceramic wall tiling; PC sum of £45/m2 to supply tiles, trims, grout and adhesive including GSPD overheads and profit allowance (PROVISIONAL QUANTITY) | 125 | m2 | 135 | 16875 | 13500 | 3375 | 0 | 0 | 16875 | 0
- | Extra over to lay stone tiles in lieu of porcelain tiles (PROVISIONAL QUANTITY) |  | m2 | 20 | Excluded - extra if required
- | Extra over to seal natural stones with sealer (PROVISIONAL QUANTITY) |  | m2 | 10 | Excluded - extra if required
- | Mastic works | 1 | Itm | 1450 | 1450
| Section total |  |  |  | 81655
.15 | CEILING FINISHES
- | Plasterboard; fixed to timber - units 6, 7 & 3 | 326 | m2 | 21 | 6846 | 2738.4 | 4107.6 | 0 | 0 | 6846 | 0
- | Skim coat plaster to plasterboard | 326 | m2 | 19 | 6194 | 4026.1 | 2167.9 | 0 | 0 | 6194 | 0
- | Lath and plaster ceiling repairs to units 1,2,4,5 & 8 | 400 | m2 | 55 | 22000
- | Cornice works\repairs (PROVISIONAL SUM) | 1 | PS | 7500 | 7500
| Section total |  |  |  | 42540
.16 | FURNITURE & FITTINGS
- | Allowance to supply and fit kitchen(s), including solid work surfaces appliances and the like (PROVISIONAL SUM) | 1 | Itm | 95000 | 95000 | 0 | 0 | 0 | 95000 | 95000 | 0
- | Allowance for built in wardrobe fixtures and fittings (PROVISIONAL SUM) | 1 | PS | 10000 | 10000
- | Allowance to supply and fit mirrors, bathroom fittings and the like - cost of fixtures and fittings included in sanitaryware provisional sum | 1 | Itm | 4000 | 4000 | 0 | 0 | 0 | 4000 | 4000 | 0
- | Allowance for fire surround, hearth and mantle; include in the allowance remedial works to fire places (PROVISIONAL SUM) | 1 | PS | 12500 | 12500
- | Allowance to supply and fit carpets including the mat to the matwell |  | PS |  | Included in floor covering
| Section total |  |  |  | 121500
.17 | PAINTING & DECORATING
- | Allowance generally for internal painting - assumed Dulux standard colours; no allowance made for any wall papering or specialist paint effects | 1 | Itm | 44950 | 44950 | 31465 | 13485 | 0 | 0 | 44950 | 0
- | Extra over allowance for clay paint to units 1-5 & 8 | 1 | Itm | 3495 | 3495
- | Extra over to strip paint from windows as lead paint present and flaking off | 68 | nr | 150 | 10200
| Section total |  |  |  | 58645
.18 | EXTERNAL WORKS (ALL PROVISONAL QUANTITIES)
- | Allowance for steps to unit 8 | 1 | Itm | 2750 | Omitted no longer required
- | Allowance for external paving's, paths, driveway, walls, patios, soft and hard landscaping ; bin store (PROVISIONAL SUM) | 1 | PS | 150000 | 150000
- | Drain pipes with allowance for bends, junctions, saddles, tapers and the like; excavating trenches, removing surplus spoil from site drainpipes in trenches 100 dia average depth n.e 1,000 (PROVISIONAL QUANTITY) | 50 | m | 120 | 6000
| Extra over for work in existing building; making good (PROVISIONAL QUANTITY) | 25 | m | 175 | 4375
- | Allowance for manholes to a maximum invert of 1000mm; plain covers NOT recessed (PROVISIONAL QUANTITY) | 4 | nr | 550 | 2200
- | Allowance for soakaway - Assumed we will reuse the existing surface water drains and soakaways | 1 | nr |  | Excluded
- | Allowance for CCTV survey existing drains (PROVISIONAL SUM) | 1 | PS | 595 | 595
- | Connect foul drain to the existing retained manhole | 1 | nr | 995 | Excluded - already connected
- | New manhole/inspection chamber; allowance for plastic preformed manholes (PROVISIONAL QUANTITY) | 4 | Nr | 600 | 2400
- | Extra over for recessed cover if required`(PROVISIONAL QUANTITY) | 4 | Nr | 225 | Optional extra if required
- | Trench for water main; (within site boundary) (PROVISIONAL QUANTITY) | 35 | m | 49 | 1715
- | Extra over for poly pipe & sand bed and surround (PROVISIONAL QUANTITY) | 35 | m | 23.51 | 822.85
- | Trench for electricity service (within site boundary) (PROVISIONAL QUANTITY) | 35 | m | 49 | 1715
- | Extra over 100mm duct and sand bed and surround (PROVISIONAL QUANTITY) | 35 | m | 27.02 | 945.7
- | Extra over for meter box and hockey stick (PROVISIONAL QUANTITY) | 8 | Nr | 150 | Assumed not require/allowed
- | Trench for gas service (within site boundary) (PROVISIONAL QUANTITY) | 35 | m | 50 | 1750
- | Extra over for meter box and hockey stick (PROVISIONAL QUANTITY) | 3 | Nr | 150 | 450
- | Trench for telecom & data service (within site boundary) (PROVISIONAL QUANTITY) | 35 | m | 49 | 1715
| Extra over for ducting and sand bed and surround (PROVISIONAL QUANTITY) | 35 | m | 25.9 | 906.5
- | Fencing; softwood; 1.80m timber fence panels (PROVISIONAL QUANTITY) |  | m | 129 | Excluded
- | Extra over for pedestrian single gate - close board (PROVISIONAL QUANTITY) |  | nr | 399 | Excluded
- | Flush drainage channels (plastic grate) - rate includes for sumps every 10m (PROVISIONAL QUANTITY) |  | m | 145 | Excluded
- | Allowance for electric gate including piers and electric supply and intercom system (PROVISIONAL SUM) |  | PS | 15000 | Excluded
- | Allowance for main services including builders work in connection
| - Mains water supply (PROVISIONAL SUM) | 8 | PS | 3000 | 24000
| - Mains electric supply (PROVISIONAL SUM) | 8 | PS | 2500 | 20000
| - Mains Gas supply (PROVISIONAL SUM) | 3 | PS | 3000 | 9000
| - BT Supply (PROVISIONAL SUM) | 8 | PS | 500 | 4000
| Section total |  |  |  | 232590.05
3.19 | PRELIMINARIES
| Skips | 44 | nr | 385 | 16940
| Plasterboard skip | 4 | nr | 595 | 2380
| Excavator | 10 | Wks | 450 | 4500
| Delivery collection | 2 | nr | 240 | 480
| Dumber | 10 | Wks | 275 | 2750
| Delivery and collection | 2 | nr | 240 | 480
| Forklift | 20 | Wks | 325 | 6500
| Delivery and collection | 2 | nr | 100 | 200
| Block splitter | 5 | wks | 20 | 100
| Delivery and collection | 2 | nr | 10 | included
| Mixer | 20 | wks | 50 | 1000
| Delivery and collection | 2 | nr | 20 | 40
| Wacker Plate | 5 | wks | 35 | 175
| Delivery | 2 | nr | 15 | 30
| Toilet | 44 | wks | 65 | 2860
| Delivery and collection | 2 | nr | 50 | 100
| Heras fencing\ hoardings | 1 | Itm | 5000 | 5000
| Delivery and collection | 2 | nr | 150 | 300
| Sundry small tools | 1 | Itm | 2500 | 2500
| Site cleaning\clearing\site welfare for sub contractors | 44 | Wks | 100 | 4400
| Tree protection | 1 | Itm |  | Excluded
| Access scaffolding | 1 | itm | 17450 | 17450
| Temporary staircase (external) | 1 | Itm | 1995 | 1995
| Loading bays | 1 | Itm | 1895 | 1895
| Towers, Youngman's etc. | 1 | Itm | 1250 | 1250
| Security | 1 | nr | 1500 | 1500
| Air test | 1 | itm |  | Assumed not required
- | Diesel | 6 | Brls | 500 | 3000
- | Genie lift | 3 | nr | 220 | 660
- | Delivery and collection | 3 | nr | 75 | 225
- | Site waste management plan | 1 | Itm | 500 | 500
- | Health and safety | 1 | Itm | 1500 | 1500
- | Temporary works - services, access etc. | 1 | Itm | 3000 | 3000
- | SAP Calculation & EPC - Design Stage |  | Itm |  | Excluded
- | SAP Calculations & EPC - Post completion phase |  | Itm |  | Excluded
- | Site office & storage | 1 | Itm | 9000 | 9000
| Delivery | 1 | Itm | 300 | 300
| Collection | 1 | Itm | 300 | 300
| Connection to services | 1 | Itm | 2000 | 2000
- | Transport | 1 | Itm | 2000 | 2000
- | Sparkle clean on completion | 9 | nr | 400 | 3600
- | Project management | 44 | Wks | 1350 | 59400
160310
ALL IN DAYWORK RATES
Labour
| Ground-worker | 44 | per hour
| Craftsman - Bricklayer, Carpenter, Painter & Decorator, Roof tiler | 44 | per hour
| Craftsman - Plasterer, Tiler | 44 | per hour
| Plumber and Gas Engineer | 49 | per hour
| Electrician | 49 | per hour
| Other trades and specialists | cost plus 20%
Hourly rate charged where operatives already on site otherwise minimum charge is 4 hours
| Plant (where plant is provided from contractors own stock cost shall be deemed to be Speedy hire internet prices current at the time of providing the works). | cost plus 20%
| Materials (where materials are provided from Contractor's stock the cost shall be deemed to be a reasonable price for the materials) | cost plus 20%
| Head Office Overhead & Profit included in the rates | 20%
| Adjustment of provisional sums and prime costs sums in addition to actual costs | 20%

## Appendix A
`
APPENDIX A DRAWINGS USED FOR PREPERATION OF QUOTATION - CONTRACT DRAWINGS
Content of appendix A
Colony Architects drawings
Planning application drawinsg prepared by Colony - 16_03_26
G S Property Developments Ltd
29 Little Heath Road
Tilehurst
Reading
RG31 5TY
Contact: Paul Spokes
Tel/Fax: 0118 9412227
Mobile: 07793 444084
Email: paul@gs-property.co.uk
.