## Miller Building
Reading Univesity Loft Project : Whiteknights Campus, Miller Buidling
Building | Task ID | Task Description | Start date | End date | Duration | Responsible Party | Dependencies | Notes
Miller - Single Storey | 1A | Parking to be provided as close to the building as possible (specifically to unload materials) | 16.06.2026 | 20.06.2026 | Each Day | Reading University | N/A
| 1B | Site Induction with BSU team and establish access points to the loft space | 16.06.2026 | 20.06.2026 | Each Day | Reading University / InstaGroup | N/A
| 1C | Material to be moved into the loft at the commencement of each workday (before 8.30am) | 16.06.2026 | 20.06.2026 | 1 Day | InstaGroup | Task 1A
| 1D | Boarding removal and enabling works (Including cable tray installation). | 16.06.2026 | 20.06.2026 | 1 Day | InstaGroup | N/A
| 1E | Loft Insulation and Ventialltion Installation and Downlights | 16.06.2026 | 20.06.2026 | 4 Days | InstaGroup | Task ID 1A, 1B, 1C & 1D
| 1F | Reboarding and tidying up | 20.06.2026 | 20.06.2026 | 1 Day | InstaGroup | Task 1E
| 1G | Reading university Sign off and building completion. | 20.06.2026 | 20.06.2026 | 1 Day | Reading University | All of the above
Miller - Two Storey | 2A | Parking to be provided as close to the building as possible (specifically to unload materials) | 20.06.2026 | 24.06.2026 | Each Day | Reading University | N/A
| 2B | Material to be moved into the loft at the commencement of each workday (before 8.30am) | 20.06.2026 | 20.06.2026 | 1 Day | InstaGroup | Task 2A
| 2C | Boarding removal and enabling works (Including cable tray installation). | 20.06.2026 | 20.06.2026 | 1 Day | InstaGroup | N/A
| 2D | Loft Insulation and Ventialltion Installation and Downlights | 20.06.2026 | 24.06.2026 | 3 Days | InstaGroup | Task ID 2A, 2B & 2C
| 2E | Reboarding and tidying up | 24.06.2026 | 24.06.2026 | 1 Day | InstaGroup | Task 2D
| 2F | Reading university Sign off and building completion. | 24.06.2026 | 24.06.2026 | 1 Day | Reading University | All of the above
| Ongoing | InstaGroup to provied an ongoing commitment to be on hand for remeditation works and queries for Six Months. | 24.06.2025 | 24.12.2026 | 6 Months | InstaGroup | All of the Above.
Weekly Meetings and Sign Off
Weekly Porgress Meetings: To take place every Monday to addresss issues and update on progress |  |  | Dates, Times and Attendees to be agreed.
Key Interfaces and Restraints
University Operations: Coordinate with University Facilities Management to create an updated programme to avoid disruptions to campus activities
Access Restrictions: Potential limited access to certain building and areas during term times or exam periods
Health & Safety: Adhere to University safety protocols and campus-specific regulations
Weather Conditions: Unlikley, but potential accounting for delays due to adverse weather during installations
Stakeholder Engagement: Ensuring regular updates to University Porject managers and stakeholders.