## Sheet1
Reading Univesity Loft Project : Whiteknights Campus
Building | Task ID | Task Description | Start date | End date | Duration | Responsible Party | Dependencies | Notes
Allen Lab | 1A | Parking to be provided as close to the building as possible (specifically to unload materials) | 05.05.2026 | 12.05.2026 | Each Day | Reading University | N/A
| 1B | Site Induction with BSU team and establish access points to the loft space | 05.05.2026 | 12.05.2026 | Each Day | Reading University / InstaGroup | N/A
| 1C | Material to be moved into the loft at the commencement of each workday (before 8.30am) | 05.05.2026 | 07.05.2026 | 1 Day | InstaGroup | Task 1A
| 1D | Boarding removal and enabling works (Including cable tray installation). | 05.05.2026 | 07.05.2026 | 1 Day | InstaGroup | N/A
| 1E | Loft Insulation and Ventialltion Installation and Downlights | 05.05.2026 | 12.05.2026 | 5 Days | InstaGroup | Task ID 1A, 1B, 1C & 1D
| 1F | Reboarding and tidying up | 12.05.2026 | 12.05.2026 | 1 Day | InstaGroup | Task 1E
| 1G | Reading university Sign off and building completion. | 12.05.2026 | 12.05.2026 | 1 Day | Reading University | All of the above
Harry Pit | 2A | Parking to be provided as close to the building as possible (specifically to unload materials) | 22.04.2026 | 25.04.2026 | Each Day | Reading University | N/A
| 2B | Material to be moved into the loft at the commencement of each workday (before 8.30am) | 22.04.2026 | 25.04.2026 | Each Day | InstaGroup | Task 2A
| 2C | Boarding removal and enabling works (Including cable tray installation). | 22.04.2026 | 25.04.2026 | 1 Day | InstaGroup | N/A
| 2D | Loft Insulation and Ventialltion Installation and Downlights | 22.04.2026 | 25.04.2026 | 4 Days | InstaGroup | Task 2A, 2B & 2C
| 2E | Reboarding and tidying up | 22.04.2026 | 25.04.2026 | 1 Day | InstaGroup | Task 2D
| 2F | Reading university Sign off and building completion. | 22.04.2026 | 25.04.2026 | 0.5 Days | Reading University | All of the above
Brian Hoskins | 3A | Parking to be provided as close to the building as possible (specifically to unload materials) | 14.04.2026 | 17.04.2026 | Each Day | Reading University | N/A
| 3B | Material to be moved into the loft at the commencement of each workday (before 8.30am) | 14.04.2026 | 17.04.2026 | Each Day | InstaGroup | Task 3A
| 3C | Boarding removal and enabling works (Including cable tray installation). | 14.04.2026 | 17.04.2026 | 1 Day | InstaGroup | N/A
| 3D | Loft Insulation and Ventialltion Installation and Downlights | 14.04.2026 | 17.04.2026 | 3 Days | InstaGroup | Task 3A, 3B & 3C
| 3E | Reboarding and tidying up | 17.04.2026 | 17.04.2026 | 1 Day | InstaGroup | Task 3D
| 3F | Reading university Sign off and building completion. | 18.04.2026 | 18.04.2026 | 1 Day | Reading University | All of the above
Psycholology | 4A | Parking to be provided as close to the building as possible (specifically to unload materials) | 28.04.2026 | 30.04.2026 | Each Day | Reading University | N/A
| 4B | Material to be moved into the loft at the commencement of each workday (before 8.30am) | 28.04.2026 | 30.04.2026 | Each Day | InstaGroup | Task 4A
| 4C | Boarding removal and enabling works (Including cable tray installation). | 28.04.2026 | 30.04.2026 | 1 Day | InstaGroup | N/A
| 4D | Loft Insulation and Ventialltion Installation and Downlights | 28.04.2026 | 30.04.2026 | 3 Days | InstaGroup | Task 4A, 4B & 4C
| 4E | Reboarding and tidying up | 30.04.2026 | 30.04.2026 | 1 Day | InstaGroup | Task 4D
| 4F | Reading university Sign off and building completion. | 01.05.2026 | 01.05.2026 | 1 Day | Reading University | All of the above
| Ongoing | InstaGroup to provied an ongoing commitment to be on hand for remeditation works and queries for Six Months. | 01.05.2026 | 01.11.2026 | 6 Months | InstaGroup | All of the Above.
Weekly Meetings and Sign Off
Weekly Porgress Meetings: To take place every Monday to addresss issues and update on progress |  |  | Dates, Times and Attendees to be agreed.
Key Interfaces and Restraints
University Operations: Coordinate with University Facilities Management to create an updated programme to avoid disruptions to campus activities
Access Restrictions: Potential limited access to certain building and areas during term times or exam periods
Health & Safety: Adhere to University safety protocols and campus-specific regulations
Weather Conditions: Unlikley, but potential accounting for delays due to adverse weather during installations
Stakeholder Engagement: Ensuring regular updates to University Porject managers and stakeholders.